## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25% | my website
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2025-05-16 | 2025-07-17 | 210 | 61 | 2025-05-17 | 2025-07-22 | 300 | 65
Project 2 | Category 2 | Employee 4 | 2025-06-11 | 2025-07-12 | 400 | 31 | 2025-06-11 | 2025-07-15 | 390 | 34
Project 3 | Category 1 | Employee 2 | 2025-04-13 | 2025-06-12 | 500 | 59 | 2025-04-13 | 2025-06-25 | 500 | 72
Project 4 | Category 2 | Employee 3 | 2025-04-23 | 2025-05-03 | 250 | 10 | 2025-04-23 | 2025-05-12 | 276 | 19
Project 5 | Category 3 | Employee 2 | 2025-04-23 | 2025-06-02 | 300 | 39 | 2025-04-23 | 2025-06-08 | 310 | 45
Project 6 | Category 4 | Employee 4 | 2025-05-23 | 2025-06-02 | 500 | 9 | 2025-05-23 | 2025-06-07 | 510 | 14
Project 7 | Category 5 | Employee 1 | 2025-06-08 | 2025-07-02 | 750 | 24 | 2025-06-08 | 2025-07-07 | 790 | 29
Project 8 | Category 2 | Employee 1 | 2025-06-13 | 2025-07-22 | 450 | 39 | 2025-06-07 | 2025-07-17 | 430 | 40
Project 9 | Category 4 | Employee 1 | 2025-04-18 | 2025-05-08 | 250 | 20 | 2025-04-23 | 2025-05-03 | 200 | 10
Row Labels | Sum of Estimated duration (in days) | Sum of Estimated work (in hours)
Employee 1 | 144 | 1660
Employee 2 | 98 | 800
Employee 4 | 40 | 900
Employee 3 | 10 | 250
Grand Total | 292 | 3610
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS