## Sheet1
Investment Area | Feature/Capability | ADO Feature Link | Current Status | DF/FF ETA | MSIT ETA | PROD ETA | Last Updated | DSB Review ETA | Contributes to X Scenario | Risks
Area1 | Investment_1 |  | Enabled at 50% in Prod/CC across plat. | Done | Done | In Prod at 50% | 2024-07-02 | N/A | Yes | ship risk
| Investment_2 |  | rolling out | Done | Done | EN-US, US Country: 100% ; T1:mid-July | 2024-07-02 | N/A | Yes
| Investment_3 |  | Development | April |  |  |  | July
| Investment_4 |  | DONE | 2024-04-05 | April | 2024-04-30
| Investment_5 |  | planning | FY25Q2 | FY25Q2 | FY25Q2
| Investment_6 |  | Code Complete | Done | Done | DONE |  | N/A | Yes
| Investment_7 |  | blocked | July | August | August |  | June | Yes
| Investment_8 |  | msit blocked | Done | July | July |  | July | Yes
| Investment_9 |  | 50% prod | Done | Done | July |  | June | Yes
| Investment_10 |  | 50% MSIT on all endpoints | Done | July | July
| Investment_11 |  | planning | Done | Done | DONE |  | N/A | Yes
| Investment_12 |  | security review | 2024-07-10 | July | August
| Investment_13 |  | exception to migrate | TBD | TBD | TBD
Area2 | Investment_1 |  | Ongoing | 2024-06-30 | N/A | N/A |  | N/A | Yes
| Investment_2 |  | Ongoing | 2024-05-31 | N/A | N/A |  | N/A | Yes
| Investment_3 |  | Ongoing | 2024-05-31 | N/A | N/A |  | N/A | Yes
| Investment_4 |  | Ongoing | N/A |  |  |  | N/A | Yes
| Investment_5 |  | Ongoing | N/A |  |  |  | N/A | Yes
| Investment_6 |  | Ongoing | N/A |  |  |  | N/A | Yes
| Investment_7 |  | Ongoing | N/A |  |  |  | N/A | Yes
| Investment_8 |  | Investigating | TBD |  |  |  | N/A | Yes
| Investment_9 |  | Rolling out | 2024-04-30 | 2024-06-19 | 2024-08-12 | 2024-07-29 | 2024-07-10
| Investment_10 |  | Development | 2024-07-17 | Mid-August | End of September | 2024-07-29 | TBD |  | Localization of test collateral by shared team is taking longer than expected (blocks quality evals and DSB)
| Investment_11 |  | Development | 2024-07-17 | Mid-August | End of September | 2024-07-29 | TBD |  | Localization of test collateral by shared team is taking longer than expected (blocks quality evals and DSB)
| Investment_12 |  | Code Complete | March | April | April | April | N/A | Yes
| Investment_13 |  | Development | April | May | May | April | N/A | Yes
| Investment_14 |  | Code Complete | March | April | April | April | N/A | Yes
Area3 | Investment_1 |  | Code Complete | February | March | May | 2024-05-16 | N/A | Yes
| Investment_2 |  | Code Complete | April | May | June | April | N/A | Yes
| Investment_3 |  | Code Complete | March | April | June | 2024-05-16 | N/A | Yes
| Investment_4 |  | Planning | May | June | June | April | N/A | Yes
| Investment_5 |  | Early engineering prototyping/investigation | June |  |  | 2024-05-16 | N/A | Yes
| Investment_6 |  | N/A |  |  |  | 2024-05-16 | N/A | Yes
| Investment_7 |  | Postponed to FY25 |  |  |  | April | N/A
Area4 | Investment_1 |  | Code Complete | February | March | April | April | N/A
| Investment_2 |  | Development | April | May | June | April | N/A
| Investment_3 |  | Development | April | May | June | April | N/A
| Investment_4 |  | Development | May | June |  | April | N/A
Commanding | Investment_1 |  | DONE | 2024-04-30 | 2024-05-15 | 2024-05-31 |  | June | Yes
| Investment_2 |  | Development - | 2024-04-22 | 2024-05-01 | 2024-05-15 |  |  | Yes
| Investment_3 |  | Development | 2024-05-06 | 5/30 50% | June |  |  | Yes (unblocks Enterprise search)
| Investment_4 |  | Development | 2024-05-06 | 5/30 50% | June |  |  | Yes
| Investment_5 |  | Development | 2024-04-30 | 2024-05-17 | June
| Investment_6 |  | Development | 2024-05-15 | June | June |  |  | Yes
| Investment_7 |  | Paused | Post H2 | Post H2 | Post H2
Area5 | Investment_1 |  | Development | Ongoing | Ongoing | Ongoing |  | Done | Yes
| Investment_2 |  | Code Complete | Done | Done | Done (all platforms, all env (including MEC) |  | Done | Yes
| Investment_3 |  | Code Complete | Done | Done | Done (All platforms, all env, rolling to MEC) |  | Done | Yes
| Investment_4 |  | Planning/Development | Ongoing | Ongoing | Ongoing |  | (need info from vertical) | Yes
| Investment_5 |  | Planning | May? |  |  |  | (need info from vertical) | Yes
| Investment_6 |  | Pending on Intent to reach FF/MSIT | 2024-07-11 | 2024-07-31 | August (start roll out) |  | Done | Yes
| Investment_7 |  | Planning | Not funded
| Investment_8 |  | Development | 2024-04-05 | April | April/Early May |  | June | Yes
Area6 | Investment_1 |  | Code Complete | Done | Done | N/A |  | July | Yes
| Investment_2 |  | Development | June | July | September |  | July | Yes
| Investment_3 |  | Development | June | July | September |  | July | Yes
| Investment_4 |  | Planning | FY25Q2
| Investment_5 |  | Code Complete | Done | Done | DONE
| Investment_6 |  | Development | Done | July | July |  |  |  | The production ETA of end of May is at risk due to issues with Chat History.
| Investment_7 |  | Planning
| Investment_8 |  | Development | Done | Done | July |  | (need info from vertical)
| Investment_9 |  | Development | May | H2 | N/A |  | (need info from vertical)
Area7 | Investment_1 |  | Prototyping | Aug/Sep |  |  |  | (need info from vertical)
Area8 | Investment_1 |  | Code Complete | Done | Done | DONE |  | (need info from vertical) | Yes
| Investment_2 |  | Development | April May | May June | June |  | June | Yes
| Investment_3 |  | Development | May June | June Post H2 | Post H2 |  |  | Yes
| Investment_4 |  | Development | May | June | June |  |  | Yes
| Investment_5 |  | Development | April | May | June |  |  | Yes
| Investment_6 |  | Code Complete | Done | April | June
| Investment_7 |  | Canceled for H2 | Post H2 | Post H2 | Post H2
| Investment_8 |  | Development - v1 in testing | June | Post H2 | Post H2
Area9 | Investment_1 |  | Canceled | Done | N/A | N/A
| Investment_2 |  | Development, dogfood in late May | Dark, ETA late may | Post H2 | Post H2 |  | TBD
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ben Rampson @Mar Gines Marin @Urmi Gupta @Jim Maiolo @KC Lemson @Irena Berezovsky @Guy Hunkin @Kaycee Reineke @Avani Reddy @David Monroy @Carlos Otero I need this Table completed (at least to Dogfood estimation) by 2/12/24. This is a critical indication of our roadmap which will help us communicate with leadership and field. It is understood that timing can change but please do you best to add realistic dates here. Reach out to you management or me if for some reason this can't be accomplished. Reply: Hi folks - can you please ensure this is up to date? I’d like to understand what capabilities are not available in production (and therefore can’t be accrued to GA readiness)
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ben Rampson @Mar Gines Marin Can you please help me to get the data here? Reply: Note: we removed the scalable for more object types context item because it's a design goal, it has no user-facing release in this FY
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Urmi Gupta , will we be able to dogfood this before the intent work is done? Reply: Fixed the date based on the latest update from the intent crew.
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alfredo Arnaiz , is TLR in MSIT already? Do you have an ETA for Prod? Reply: It's 100% MSIT, on track for 10% Prod on 3/25
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alfredo Arnaiz , can we enumerate any UX risks, for instance, do we have a plan to be clear with users on supported vs unsupported TLRs?
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @KC Lemson I noticed that we don't have language support on this list
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Evaluation/testing pipelines aren't customer facing and are used internally only so no DF/MSIT/Prod ETAs but just ship ETA.
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Evaluation/testing pipelines aren't customer facing and are used internally only so no DF/MSIT/Prod ETAs but just ship ETA.
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Evaluation/testing pipelines aren't customer facing and are used internally only so no DF/MSIT/Prod ETAs but just ship ETA.
Note on G33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Chirag Fifadra Is this still on for April? Reply: The context menu entrypoint just hit DF in web and Win32 this week, and we still need to validate the telemetry and fix some bugs. MSIT in April seems unlikely. FYI @KC Lemson, @Devin Devlin
Note on F35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Colored yellow and with a question mark because there are still technical feasibility questions being worked through
Note on F37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The original plan for summarize text UX was to have full e2e experience on grid without chat pane support, but as we had to scope down the H2 UX plans, this ended up having a trickle-down impact on the plans for the Skill work.
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Irena Berezovsky , Alfredo is trying to add info on RAI reviews needed and was asking for these rows to be split by existing vertical capability vs new capability. Something like Calculated Rows will require a new DSB review (as Alfredo/Lev are discussing). Is there a separate row for Calculated Rows? Reply: Yes. Somehow the text was corrupted. I fixed the Feature/Capability description.
Note on E53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging shared U/X control work
Note on F53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Irena Berezovsky IIUC the plan is for the shared team or deliver this, right? Should we remove this line, or adjust date per shared delivery plan?
Note on F55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @depends on funding started April 1.
Note on F56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shipped as part of larger else skill
Note on H57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Guy Hunkin , Alfredo and I were reviewing the DSB review dates against prod dates - can you help ensure the Search Prod dates are updated? Reply: Updated for Search. @Odi Paneth , @Gal Horowitz , @Dror Yashar - please update Reply: @Urmi Gupta Looks good to me.
Note on F72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rowan Armstrong fyi that I put this in as a placeholder for now (question mark is my way of saying this is PM handwaving) Reply: @KC Lemson @Ehab Sobhy @Carlos Otero I separated these lines into the skill, on-grid, and full chat based on the discussion today
Note on E73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @KC Lemson switching this one (Summarize text on-grid experience) to canceled for H2 per the latest discussion.s
Note on F73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Rowan Armstrong fyi that I put this in as a placeholder for now (question mark is my way of saying this is PM handwaving)