## Panzhihua Maintenance Work Area
Sichuan Province Xichang to Panzhihua Expressway Project
Division and Subdivision Engineering Classification Table
Contractor: Panzhihua Highway Construction Co., Ltd. Contract No.: FJ4
Supervision Unit: Sichuan Highway Engineering Supervision Office
Sub-unit Project Name: Panzhihua Maintenance Work Area
Division Engineering | Sub-division Engineering | Serial No. | Sub-item Engineering | Inspection Batch
Foundation and Basic Engineering | Unreinforced Earthwork | 1 | Earthwork Excavation | Earthwork Excavation
|  | 2 | Earthwork Backfill | Earthwork Backfill
| Foundation and Treatment | 1 | Sand and Gravel Foundation | Sand and Gravel Foundation
| Masonry Foundation | 1 | Brick Masonry | Brick Masonry
| Concrete Foundation | 1 | Formwork | Foundation Cushion, Independent Column Foundation Cap, Foundation Frame Column, Foundation Beam
|  | 2 | Rebar | Independent Column Foundation Cap, Foundation Frame Column, Foundation Beam
|  | 3 | Concrete | Foundation Cushion, Independent Column Foundation Cap, Foundation Frame Column, Foundation Beam
Main Structure | Concrete Structure | 1 | Formwork | Frame Column, Structural Column, Canopy, Second Floor Decorative Column
Roof Frame Beam, Slab, Second Floor Decorative Beam
|  | 2 | Rebar | Frame Column, Structural Column, Canopy, Second Floor Decorative Column
Roof Frame Beam, Slab, Second Floor Decorative Beam
|  | 3 | Concrete | Frame Column, Structural Column, Canopy, Second Floor Decorative Column
Roof Frame Beam, Slab, Second Floor Decorative Beam
| Masonry Structure | 1 | Infill Wall Masonry | Infill Wall Masonry, Parapet
Building Decoration and Finishing | Floor | 1 | Integral Surface Layer (Cement Pebble Surface Layer) | Cement Pebble Floor
|  |  | Integral Surface Layer (Cement Concrete Surface Layer) | Splash
|  |  | Integral Surface Layer (Cement Mortar Surface Layer) | Hidden Gutter and Ramp
|  | 2 | Tile Surface Layer (Brick Surface Layer) | Brick Surface Layer
|  |  | Tile Surface Layer (Granite Surface Layer) | Lobby and Granite Surface Layer
| Plastering | 1 | General Plastering | Interior Wall, Ceiling Plastering, Exterior Wall Plastering
| Doors and Windows | 1 | Wooden Door and Window Fabrication and Installation | Wooden Door and Window Fabrication and Installation
|  | 2 | Metal Door and Window Installation | Metal Door and Window Installation
|  | 3 | PVC Window | PVC Window Installation
|  | 4 | Door and Window Glass Installation | Door and Window Glass Installation
| Facing Tile (Brick) | 1 | Facing Tile Adhesion | Bathroom, Exterior Wall
| Painting | 1 | Water-based Paint Coating | Wall, Ceiling Emulsion Paint
| Ceiling | 1 | Concealed Frame Ceiling | Aluminum Alloy Square Panel Ceiling, Gypsum Board Ceiling
Building Roofing | Membrane Waterproof Roofing | 1 | Insulation Layer, Leveling Layer | Insulation Layer, Leveling Layer
|  | 2 | Membrane Waterproof Layer | Membrane Waterproof Layer
Building Water Supply and Drainage | Indoor Water Supply System | 1 | Indoor Water Supply Pipes and Fittings Installation | Indoor Water Supply Pipes and Fittings Installation
|  | 2 | Indoor Fire Hydrant System Installation | Indoor Fire Hydrant System Installation
| Indoor Drainage System | 1 | Indoor Drainage Pipes and Fittings Installation | Indoor Drainage Pipes and Fittings Installation
|  | 2 | Rainwater Pipes and Fittings Installation | Rainwater Pipes and Fittings Installation
| Sanitary Ware Installation | 1 | Sanitary Ware Installation | Sanitary Ware Installation
|  | 2 | Sanitary Ware Water Supply Fittings Installation | Sanitary Ware Water Supply Fittings Installation
|  | 3 | Sanitary Ware Drainage Pipes Installation | Sanitary Ware Drainage Pipes Installation
Building Electrical | Electrical Lighting Installation | 1 | Complete Distribution Cabinet, Control Cabinet (Panel, Desk) and Power Lighting Distribution Box (Panel) Installation | Complete Distribution Cabinet, Control Cabinet (Panel, Desk) and Power Lighting Distribution Box (Panel) Installation
|  | 2 | Electrical Conduit, Cable Conduit and Trunking Installation | Electrical Conduit, Cable Conduit and Trunking Installation
|  | 3 | Electrical Wire, Cable Conduit and Trunking Installation | Electrical Wire, Cable Conduit and Trunking Installation
|  | 4 | Ordinary Lighting Fixture Installation | Ordinary Lighting Fixture Installation
|  | 5 | Socket, Switch, Fan Installation | Socket, Switch, Fan Installation
|  | 6 | Building Lighting Power-on Test Run | Building Lighting Power-on Test Run
| Lightning Protection and Grounding Installation | 1 | Grounding Device Installation | Grounding Device Installation
|  | 2 | Lightning Down Conductor and Substation Grounding Main Line Installation | Lightning Down Conductor and Substation Grounding Main Line Installation
|  | 3 | Building Equipotential Bonding | Building Equipotential Bonding
|  | 4 | Lightning Arrester Installation | Lightning Arrester Installation