## Direct labour man-hours
Project: | xx |  |  |  | VK
Project Number: | xx |  |  |  | 2015-12-09
Location: | xx |  |  |  | 0
4Q 2015
AACEI Class 5
Major Onshore Project
INDICATIVE
Key Quantities & Direct Labour Hours
Description | Remarks | Unit | Key Qty example only (Use own project) | Hours / Key Qty (Rough) | Notes
Equipment | Total number of different kinds of process / mechanical equipment | Nos | 150 | 2500 | Manhours for installing all mechanical & process equipment
Civil works | Total concrete volume | m3 | 50000 | 50 | Manhours for all civil works including site clearance, excavation, concrete, trenches, roads etc.
Steelwork | Total steel tonnage | Tonne | 15000 | 100 | Manhours for all steelworks
Buildings | Total plot area of all buildings | m2 | 10000 | 100 | Manhours for all building works
Piping | Total length of all piping | m | 100000 | 50 | Manhours for all piping fabrication and installation including all small bore piping. Piping hours per unit will vary considerably with pressure rating, amount for large bore piping, piping material, plot layout, amount of valving etc.
Electrical cables | Total length of all electrical cables | m | 500000 | 2 | Installation of all electrical cables, cable trays (if any), all electrical equipment, lighting, earthing etc.
Instrumentation cables | Total length of all instrument cables | m | 500000 | 1 | Installation of all field instruments, instrument cables, instrument tubing and fittings etc.
Notes:
These are anecdotal numbers for a quick calculation of total direct labour hours for a major onshore project
This can be used as a high level benchmark, cross-check and a rough guide
Indirect hours could be calculated as a percentage of the direct hours, roughly say 30-40% of the direct hours.
The estimated hours for individual projects will depend on several design parameters, plot layout, location, labour productivity and many other factors
A more detailed estimating work should still be performed if estimating resource is available