## Sheet1
[6 empty] | Estimated Costs | [28 empty] | Actual Costs
Project ID | Client | Project type | Start date | End date | Lead contractor | Land acquisition | Site surveys and testing | Permit fees and approvals | Design and engineering fees | Clearing and excavation | Temporary access roads | Concrete and reinforcement | Waterproofing | Wood framing | Roofing system | Windows and glazing | Exterior walls and siding | Drywall and painting | Flooring | Ceilings | HVAC system | Electrical wiring | Plumbing systems | General conditions | Project management | Insurance and bonding | Contingency (10%) | Sustainability features | Landscaping | Signage | Contractor overhead | Final cleanup | System commissioning | Warranty & documentation | Land acquisition2 | Site surveys and testing2 | Permit fees and approvals2 | Design and engineering fees2 | Clearing and excavation2 | Temporary access Roads2 | Concrete and reinforcement2 | Waterproofing2 | Wood framing2 | Roofing system2 | Windows and glazing2 | Exterior walls and siding12 | Drywall and painting13 | Flooring14 | Ceilings15 | HVAC system16 | Electrical wiring17 | Plumbing systems18 | General conditions19 | Project management20 | Insurance and bonding21 | Contingency (10%)22 | Sustainability features23 | Landscaping24 | Signage25 | Contractor overhead26 | Final cleanup28 | System commissioning29 | Warranty & documentation30
58849 | NorthBridge Property Group | Commercial | 2023-01-01 | 2024-04-01 | Logan Pierce | 287500 | 16500 | 13680 | 46000 | 33900 | 11200 | 68400 | 9120 | 135600 | 51300 | 40250 | 44000 | 34200 | 27500 | 17250 | 55500 | 33300 | 31640 | 22800 | 28000 | 17100 | 55500 | 77000 | 34200 | 22000 | 5600 | 46000 | 9200 | 346830.4 | 277500 | 17100 | 13440 | 44400 | 42336 | 11500 | 83250 | 9120 | 132000 | 50850 | 39550 | 46000 | 34200 | 28500 | 17250 | 55500 | 34200 | 30800 | 22200 | 27500 | 21696 | 57500 | 79100 | 40320 | 22400 | 5600 | 51076 | 8880 | 340637
10573 | CrestPoint Commercial Services | Commercial | 2023-02-01 | 2025-01-01 | Connor Reeves | 311584.77 | 19936.71 | 13605.2 | 51765.28 | 40004.26 | 11259.32 | 79339.47 | 9887.5 | 143716.65 | 51419.64 | 36237.97 | 48503.58 | 30871.6 | 27657.88 | 19849.58 | 62843.64 | 40255.68 | 30031.1 | 22235.01 | 25871.35 | 15127.84 | 67115.22 | 93439.7 | 37369.2 | 20259.72 | 6512.19 | 46639.4 | 8770.3 | 394721.6 | 322813.05 | 20475.54 | 13725.6 | 51303.09 | 47205.0268 | 11259.32 | 102347.9163 | 10062.5 | 139967.52 | 52809.36 | 36237.97 | 47227.17 | 30598.4 | 27902.64 | 20025.24 | 63394.9 | 40608.8 | 30031.1 | 21841.47 | 25871.35 | 19882.304 | 65333.4 | 93439.7 | 43365.258 | 20442.24 | 6454.56 | 52236.128 | 9009.49 | 391197.3
68346 | AtlasCore Management | Commercial | 2023-03-14 | 2024-12-14 | Julian Hayes | 321865.81 | 18403.84 | 12971.46 | 48497.12 | 38468.59 | 13124.1 | 73890.88 | 8352.96 | 122149.95 | 57566.82 | 46145 | 46380.4 | 31552.55 | 28210.6 | 17190.8 | 53482 | 33129.34 | 35466.18 | 24737.46 | 29481.6 | 15161.44 | 67959.96 | 83906.28 | 39043.4 | 22816 | 5208.35 | 42372.03 | 10419 | 342020.97 | 313320.7 | 18239.52 | 13322.04 | 48930.13 | 48123.1848 | 13243.41 | 86491.914 | 8427.54 | 125451.3 | 58085.44 | 46984 | 46802.04 | 30729.44 | 28723.52 | 17659.64 | 55426.8 | 33129.34 | 35466.18 | 24960.32 | 29747.2 | 18951.8 | 67363.82 | 80962.2 | 51679.264 | 22816 | 5163.06 | 48311.7488 | 10237.8 | 338939.7
34655 | Stonegate Realty Solutions | Commercial | 2023-04-11 | 2024-06-11 | Miles Thornton | 277933.7 | 19108.1 | 14837.37 | 50769.77 | 36553.44 | 12318.8 | 79060.8 | 10670.85 | 137969.67 | 52312.08 | 43431.55 | 52835.41 | 38046.4 | 28253.2 | 19858.2 | 58333.99 | 38371.2 | 30677.4 | 26662.72 | 29452.32 | 15703.25 | 53711.16 | 91676.2 | 36720.48 | 22082.94 | 6415.92 | 47685 | 8337.21 | 358862.88 | 285513.71 | 19976.65 | 14837.37 | 49421.9 | 42747.9426 | 11890.32 | 98225.985 | 10299.69 | 142941.55 | 53254.64 | 42662.85 | 52367.84 | 38386.1 | 28007.52 | 19340.16 | 58333.99 | 37686 | 29601 | 27138.84 | 28670.4 | 19881.68 | 53235.84 | 93343.04 | 43697.3712 | 22082.94 | 6190.8 | 54837.75 | 8337.21 | 355714.96
13167 | HorizonPeak Asset Group | Commercial | 2023-05-20 | 2025-03-20 | Brandon Knox | 255139.05 | 18929.94 | 14881.44 | 46568.5 | 32425.35 | 12582.18 | 67767.3 | 8379.39 | 128550.4 | 49448.28 | 41938.82 | 51931.04 | 35916.1 | 31243.37 | 15245.44 | 63498 | 32400.1 | 34199 | 23432.81 | 29490.66 | 18593.02 | 60472.75 | 90025.97 | 31098.87 | 21155.68 | 6532.9 | 40889.05 | 9189.16 | 375905.94 | 252840.5 | 19271.02 | 14615.7 | 46991.85 | 38244.696 | 12140.7 | 88097.49 | 8454.88 | 128550.4 | 49448.28 | 40825.4 | 51467.37 | 36895.63 | 31796.35 | 15245.44 | 61827 | 31273.14 | 35131.7 | 22810.7 | 29490.66 | 23799.0656 | 60472.75 | 89229.28 | 37696.8735 | 21344.57 | 6829.85 | 46190.1525 | 9107.84 | 375905.94
32365 | Ironwood Property Services | Commercial | 2023-06-11 | 2024-08-11 | Logan Pierce | 282772.6 | 18274.3 | 13101.95 | 51666.05 | 36975.95 | 11339.76 | 71322.9 | 10413.7 | 131045.95 | 60039.24 | 39743 | 45494 | 32402.75 | 27700.05 | 19633.9 | 55823.13 | 34328 | 34202.56 | 25256 | 32019.9 | 17997.18 | 66884 | 73802.3 | 37287.12 | 25000.2 | 6229.69 | 50873.64 | 10934.88 | 367769.8 | 282772.6 | 18274.3 | 12646.23 | 51216.78 | 47232.757 | 11544.08 | 91500.7968 | 10413.7 | 127627.36 | 60039.24 | 40104.3 | 44702.8 | 32689.5 | 26977.44 | 20347.86 | 55329.12 | 34634.5 | 33897.18 | 26404 | 32019.9 | 22496.475 | 65720.8 | 75815.09 | 48048.052 | 24342.3 | 6119.43 | 56451.89 | 10551.2 | 367769.8
49243 | MetroVista Holdings | Commercial | 2023-07-12 | 2024-10-12 | Connor Reeves | 264960.33 | 17826.18 | 12236 | 47451.3 | 32502.19 | 11389.71 | 78715.8 | 10277.3 | 141510.6 | 47747.7 | 36764.55 | 41924.7 | 37584.93 | 25583.8 | 16032.15 | 61987.95 | 32143.1 | 30496.14 | 26221.14 | 29620.8 | 15791.28 | 58961.1 | 77230.44 | 35219.16 | 26018.72 | 6627.81 | 51065.55 | 10339.8 | 317545.82 | 264960.33 | 17357.07 | 12345.25 | 46213.44 | 40912.4912 | 11492.32 | 97524 | 10277.3 | 144083.52 | 47747.7 | 36439.2 | 43057.8 | 37917.54 | 26281.54 | 15613.92 | 63104.85 | 33019.73 | 31045.62 | 25301.1 | 29890.08 | 20390.144 | 59497.11 | 75198.06 | 40146.753 | 26018.72 | 6806.94 | 57704.0715 | 10067.7 | 309115.4
73949 | CobaltEdge Realty Partners | Commercial | 2023-07-24 | 2025-01-24 | Julian Hayes | 334533 | 15880.2 | 14050.42 | 45325.28 | 31667.12 | 11627.65 | 68798.24 | 8641.2 | 154466.48 | 58652.4 | 43486.3 | 50903.28 | 34904.1 | 32160.03 | 15811.8 | 62056.77 | 31204.8 | 37001.44 | 20899.62 | 30477.23 | 18681.75 | 53820.8 | 73650.5 | 34204.8 | 22315.7 | 6559.3 | 41785.14 | 10780.2 | 363529.6 | 331598.5 | 15740.9 | 13926.08 | 45325.28 | 37058.9376 | 11627.65 | 86593.6419 | 8717 | 150365.6 | 58652.4 | 43486.3 | 51349.8 | 34904.1 | 32449.76 | 15534.4 | 64293.05 | 31488.48 | 36340.7 | 21082.95 | 30477.23 | 23230.35 | 55288.64 | 74989.6 | 40386.096 | 23330.05 | 6559.3 | 46385.2032 | 10589.4 | 357038
72082 | CivicOak Property Advisors | Commercial | 2023-09-04 |  | Miles Thornton | 337002.9 | 16317.35 | 15997.62 | 48626.6 | 33618.6 | 12267.54 | 61346.37 | 9563.19 | 153611.07 | 52407.04 | 41452.68 | 54051.96 | 35853 | 29966.47 | 15209.6 | 66774.36 | 34924.35 | 35329.45 | 21805.3 | 32258.6 | 19473.84 | 61533.92 | 69998.82 | 39986.65 | 23817.65 | 5439.82 | 49369.6 | 10376.3 | 377524 | 322350.6 | 15891.68 | 15436.3 | 49510.72 | 42226.731 | 11837.1 | 71128.629 | 9732.45 | 152251.68 | 52874.96 | 41816.3 | 53577.82 | 36499 | 29170.9 | 15481.2 | 64431.4 | 34316.97 | 35954.75 | 22003.53 | 32258.6 | 26228.28 | 60984.51 | 70629.44 | 45981.1704 | 23196.32 | 5439.82 | 55787.648 | 10470.63 | 384265.5
71855 | SummitLine Commercial Estates | Commercial | 2023-10-30 |  | Brandon Knox | 281509.65 | 18206.1 | 13068.45 | 51097.08 | 33548.9 | 10816.9 | 61703.79 | 8449.05 | 123140.07 | 55358.7 | 42452.3 | 43228.9 | 39809.04 | 32520.4 | 16463.7 | 52350.1 | 30830.25 | 33103.35 | 23378.3 | 30383.36 | 15974.2 | 65772.78 | 77138.1 | 36086.1 | 21485.58 | 6223.8 | 46625.6 | 9264.64 | 381831.52 | 269270.1 | 18371.61 | 13299.75 | 50648.86 | 42994.4403 | 10816.9 | 72237.9055 | 8228.64 | 125358.81 | 54395.94 | 43224.16 | 44407.87 | 40167.68 | 33702.96 | 16763.04 | 52826.01 | 31385.75 | 32224.5 | 24228.42 | 30654.64 | 20287.234 | 66936.9 | 75784.8 | 42555.59 | 21297.11 | 6115.56 | 49504.224 | 9430.08 | 381831.52
17207 | VanguardSquare Management | Commercial | 2023-11-15 |  | Logan Pierce | 281886.66 | 18507.5 | 14740.8 | 41751.36 | 32481.12 | 11169.76 | 61284.42 | 10469.8 | 145297.56 | 45438.8 | 42146.7 | 44812.41 | 34540.25 | 26328.5 | 18838.5 | 64442.56 | 37622.28 | 34246.83 | 22149.13 | 32265.48 | 16388.64 | 62451.71 | 73387.85 | 33686.4 | 20125.6 | 5449.85 | 51852.9 | 10546.65 | 336988.6 | 281886.66 | 18844 | 15006.4 | 40286.4 | 38681.5338 | 10970.3 | 77961.375 | 10660.16 | 140199.4 | 45851.88 | 42906.1 | 45208.98 | 33939.55 | 27525.25 | 18508 | 65017.94 | 37622.28 | 34246.83 | 22345.14 | 31974.8 | 20813.5728 | 61899.04 | 72088.95 | 41844.6336 | 20857.44 | 5260.29 | 57538.525 | 10088.1 | 331024.2
13438 | Elena Foster | Residential | 2023-01-13 | 2024-08-13 | Connor Reeves | 0 | 5600 | 3360 | 11300 | 9120 | 3360 | 16950 | 2825 | 27750 | 8880 | 7910 | 9900 | 9200 | 8050 | 4560 | 11000 | 8800 | 10170 | 5550 | 6840 | 4520 | 11200 | 5700 | 4600 | 1140 | 6660 | 2260 | 3330 | 1665 | 0 | 5650 | 3390 | 11400 | 11592 | 3360 | 21217.5 | 2875 | 28750 | 9120 | 7770 | 10080 | 9040 | 7910 | 4560 | 11000 | 8960 | 10350 | 5700 | 6780 | 5683.2 | 11000 | 5600 | 5420.8 | 1110 | 6840 | 2553.8 | 3360 | 1650
74952 | Bryce Chandler | Residential | 2023-02-14 | 2024-06-14 | Julian Hayes | 0 | 5978.85 | 3074.4 | 11652.95 | 9331.3 | 2836.05 | 17592.96 | 2927.07 | 25422.88 | 8108.82 | 7987.84 | 9205.75 | 9923.66 | 9136.75 | 4318.72 | 11902.53 | 10096.8 | 8602.5 | 4860.9 | 7140 | 4364.64 | 12874.25 | 5300.35 | 5153.15 | 994.4 | 7793.04 | 1931.17 | 3500.2 | 1770.71 | 0 | 5718.9 | 3046.95 | 11247.63 | 12365.6691 | 2861.6 | 20407.8336 | 3032.55 | 25422.88 | 8037.69 | 8059.16 | 9045.65 | 10099.3 | 8977.85 | 4318.72 | 11902.53 | 10277.1 | 8525 | 5037.66 | 7076.25 | 5592.5847 | 12650.35 | 5162.08 | 6338.3745 | 985.6 | 7724.68 | 2143.086 | 3500.2 | 1786.38
12189 | Naomi Sinclair | Residential | 2023-03-30 | 2024-06-30 | Miles Thornton | 0 | 5458.2 | 3471.36 | 12142.85 | 9159.72 | 3207.96 | 18557.99 | 3053.12 | 28952 | 8180.7 | 8845.26 | 8896.8 | 10142.58 | 7244.6 | 4442.9 | 12673 | 9181.92 | 10522.8 | 6229.55 | 6105.39 | 4046.85 | 10091.4 | 5100.82 | 4994.08 | 1151.47 | 7430.88 | 2098.41 | 3068.2 | 1565.22 | 0 | 5507.82 | 3409.92 | 12142.85 | 11552.8 | 3151.68 | 21341.6885 | 3107.64 | 28435 | 8401.8 | 8612.49 | 9139.44 | 10142.58 | 7508.04 | 4644.85 | 12673 | 9264.64 | 10902 | 6175.38 | 6159.42 | 5038.8561 | 10458.36 | 4965.4 | 5895.2439 | 1151.47 | 7496.64 | 2329.2351 | 2961.48 | 1551.49
95209 | Jared Whitman | Residential | 2023-04-16 |  | Brandon Knox | 0 | 5215.25 | 3110.8 | 12095.67 | 8390.4 | 2911.7 | 16449.6 | 2597.4 | 30622.9 | 9459.9 | 7797 | 11045.75 | 8178.48 | 8178.36 | 3865.02 | 11554.05 | 9566.85 | 9652.56 | 5424.16 | 6925.3 | 5017.6 | 11274.6 | 4946.46 | 4148.1 | 1132.75 | 5929.11 | 2112.32 | 3065.44 | 1488.1 | 0 | 5215.25 | 3167.36 | 12095.67 | 10716.16 | 2991.11 | 20826.624 | 2644.2 | 30901.29 | 9130.86 | 7797 | 10661.55 | 8178.48 | 8250.1 | 3830.2 | 11152.17 | 9150.9 | 9826.48 | 5327.3 | 6684.42 | 6588.288 | 10882.44 | 4772.9 | 5106.6882 | 1122.9 | 5929.11 | 2386.5444 | 3010.7 | 1488.1
88676 | Isabella Cruz | Residential | 2023-06-14 | 2024-07-14 | Logan Pierce | 0 | 5334.73 | 3371.5 | 10912.08 | 9612.48 | 3160.2 | 14854.55 | 2851.59 | 28872.78 | 9362.15 | 8579 | 9425.33 | 7686.8 | 8976.8 | 4963.92 | 11806.24 | 9514.44 | 9848.46 | 5284.16 | 6625.19 | 3969.28 | 11434.5 | 5728.8 | 4805.1 | 988.75 | 6323.52 | 1975.68 | 3606.96 | 1797.6 | 0 | 5381.94 | 3371.5 | 10529.2 | 11615.9232 | 3022.8 | 17505.1184 | 2851.59 | 27859.7 | 9117.92 | 8504.4 | 9258.51 | 7896.44 | 9217.25 | 5053.36 | 11597.28 | 9264.06 | 9848.46 | 5425.7 | 6625.19 | 4956.6384 | 11642.4 | 5832.96 | 5895.099 | 962.5 | 6492.9 | 2173.248 | 3575.32 | 1829.7
43163 | Gavin Mercer | Residential | 2023-06-30 | 2024-11-30 | Connor Reeves | 0 | 4974.9 | 3309.6 | 13070.1 | 9621.6 | 3496.64 | 16292.64 | 3173.04 | 28016.8 | 8674.45 | 6957.5 | 9034.35 | 9093.05 | 7095 | 4081.47 | 11751.85 | 8781.23 | 11000.64 | 5569.77 | 6003.2 | 4563.2 | 10138.7 | 5190.09 | 5100.45 | 1216.6 | 7559.2 | 2086.7 | 3608.64 | 1489.34 | 0 | 4888.38 | 3250.5 | 12611.5 | 10867.344 | 3559.08 | 19877.0208 | 3088.8 | 28767.25 | 8372.73 | 6836.5 | 8954.4 | 8776.77 | 7417.5 | 4044.7 | 11240.9 | 8703.52 | 11197.08 | 5471.19 | 5896 | 5790.1056 | 10230.87 | 5236.02 | 6638.856 | 1260.84 | 7696.64 | 2399.705 | 3576.42 | 1449.8
81483 | Talia Bennett | Residential | 2023-07-11 | 2024-11-11 | Julian Hayes | 0 | 5586.72 | 3342.9 | 9853.2 | 9251.85 | 3736.35 | 18863.09 | 3021.42 | 27419.84 | 8025.3 | 8498.6 | 9585.4 | 8243.4 | 7302.9 | 4587 | 10516.14 | 10483.44 | 8983.8 | 5791.5 | 7470.4 | 5101.95 | 11375.8 | 4938.48 | 3936.92 | 964.32 | 6982.5 | 2000.9 | 3671.94 | 1692.9 | 0 | 5586.72 | 3494.85 | 9424.8 | 10917.183 | 3703.86 | 22824.3389 | 2994.2 | 27909.48 | 8169.9 | 8884.9 | 9933.96 | 8243.4 | 7634.85 | 4670.4 | 10610.88 | 10483.44 | 8827.56 | 5791.5 | 7470.4 | 6364.7955 | 11276.88 | 4851.84 | 4687.722 | 947.1 | 6737.5 | 2321.9535 | 3543.1 | 1769.85
70368 | Andre Holloway | Residential | 2023-08-20 | 2025-01-20 | Miles Thornton | 0 | 6374.33 | 3020.64 | 11527.35 | 9639.24 | 3736.32 | 14417.76 | 2824.92 | 26930.7 | 8879.15 | 7533.12 | 10987.9 | 9733.82 | 8481 | 4546.08 | 10582.88 | 9913.2 | 11124.12 | 5523.44 | 6050.15 | 4943.75 | 11478.5 | 5422.35 | 4914.56 | 1245.42 | 7565.6 | 1963.05 | 3543.15 | 1481.7 | 0 | 6317.92 | 2993.67 | 11735.05 | 11567.088 | 3836.4 | 17468.661 | 2849.7 | 25759.8 | 8879.15 | 7465.86 | 11487.35 | 9647.68 | 8866.5 | 4546.08 | 10582.88 | 9913.2 | 10733.8 | 5474.56 | 5787.1 | 6179.6875 | 11478.5 | 5617.75 | 6388.928 | 1234.2 | 7565.6 | 2178.9855 | 3450.72 | 1508.64
52559 | Kendra Lawson | Residential | 2023-09-12 | 2025-01-12 | Brandon Knox | 0 | 5475.8 | 3096.9 | 11272.8 | 9446.08 | 3569.44 | 14871.3 | 3132.64 | 31278.4 | 9413.6 | 8394.96 | 10711.27 | 10473.05 | 7121.58 | 4323.45 | 9454.5 | 7939.6 | 11700.1 | 6282.45 | 6563.04 | 4098.6 | 9710.09 | 4866.24 | 4657.5 | 1131.13 | 7261.38 | 2138.08 | 3549.33 | 1594.43 | 0 | 5575.36 | 3208.5 | 11071.5 | 11902.0608 | 3505.7 | 18223.865 | 3188.58 | 31001.6 | 9413.6 | 8247.68 | 10426.9 | 10473.05 | 6996.64 | 4401.35 | 9540.45 | 7663.44 | 11598.36 | 6173.19 | 6621.12 | 5123.25 | 9796.02 | 4997.76 | 5540.4 | 1111.11 | 7261.38 | 2352.0789 | 3517.92 | 1566.21