## Assistant2302a3b1df77 (hidden)
0

## More information (hidden)
Simple Gantt Chart (Vertex42.com)
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About this template
With this template, you can create a Gantt chart in a simple way to help you visualize and manage your projects. All you have to do is enter the task, the start date, and the end date. You don't need to enter a formula. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. To insert a new task, insert a new row.
Screen reader guide
There are two worksheets in this workbook. TimeSheet More information The description of each worksheet begins in cell A1 in column A of each worksheet. It is written in hidden text. Each step describes the information that is contained in that line. Unless explicitly indicated, each subsequent step is stored in cell A2, cell A3, and so on. For example, the descriptive text might say "Continue in cell A6" for the next step. This hidden text is not printed. If you want to remove these descriptions from the worksheet, just delete column A.
More help
Follow the link below to access Vertex42.com and learn more about how to use this template. For example, how to calculate the number of days and working days, create task dependencies, change the color of the bar, add scroll bars to easily change the week display, and expand the date range displayed in the chart.
How to use a simple Gantt chart
Other Project Management Templates
Visit Vertex42.com to download more project management templates such as different types of project schedules, Gantt charts, task lists, and more.
Project Management Template
About Vertex42
Vertex42.com offers over 300 professionally designed spreadsheet templates for businesses, homes, and education. Most of this can be downloaded for free. The Vertex42.com collection includes a variety of calendars, planners, and schedules, as well as spreadsheets of personal finances for budgeting, debt reduction, and loan repayment.
For businesses, there are invoices, timesheets, inventory management, financial statements, and project planning templates. For students and teachers, there are resources such as lesson plans, gradebooks, and attendance books. Use cartes, checklists, and exercise logs to organize your family's life. Each template has been thoroughly researched, adjusted, and refined over time based on feedback from thousands of users.

## Qualifications_Tasks and Assign
【Authentication Platform】Infrastructure Tm Issue Management Book |  |  |  |  | [Rules for this document] | [14 empty] | Status | Estimated Required Man-Hours | Estimated Required Man-Months |  | Required man-hours (super approximate) | Close/Withdrawn Exclude
[5 empty] | - Do not leave the status field blank. | [14 empty] | New | 40 | 2 |  | Total | 521 | 32.3
[5 empty] | - The owner of the assignment should be specified by name. | [14 empty] | Supported | 0 | 0
[5 empty] | - Add new information above the existing content. | [14 empty] | On Hold | 286 | 14.3 |  |  | 5.3833
[5 empty] | - Highlight additional information in red. | [14 empty] | Pending Approval | 0 | 0
[20 empty] | Closed | 84.9 | 4.245
[20 empty] | Withdrawn | 105 | 5.25
[20 empty] | Task Assigned (Start Time Pending) | 0 | 0
[20 empty] | WBS Converted To Closed | 125 | 6.25
[20 empty] | WBS Conversion To Supported | 195 | 9.75
№ | System Name: | status | Measures/Maintenance classification | Process classification | Drafting classification | Drafting date: | Presentation range | Deadline | Clients | Voter: | Person in charge: | Clients | PMWBNo | Priority | TeamsURL | Progress Report Memo | Progress±D (-delay/+front-loaded) | Overview | Details | Scheduled Tasks | Required man-hours (super approximate) | production costs (Results) | Response Status/Progress/Resolution | Responders (Name of Person) | Completion dateKanryobi | Approval Date: | Approver | Supported environment performance date (design/CDK/construction/testing) | [5 empty] | Related Materials: | Remarks:
[28 empty] | IT | Reproduction (1) | Reproduction (2) | ⁠ | Refurbished | Production
1 | XXX Management | Supported by | policy | Basic design | subject | 2024-04-24 | for the Interior | 2024-08-30 | AA | BB | BB | ー | ー | ⁠ |  | ー | ±0D | AWS CDK related - There is no way to divide the STACK (design policy) ・CDK's test automation | ■2024/09/17 BB We are preparing materials for the Digi Agency. ■2024/08/23 BB Create a CDK-enabled workload. ■2024/7/22 BB How to divide the STACK of CDK (design policy) Creation is required because there is no design document There is no CDK/cFn/manual separation in the design document that can be understood. | ・CDK document structure ・CDK-related diagram (image of class diagram) ・CDK/cFn/Manual Residence Separation | 180 | [14 empty] | ー
2 | XXX Management | hold | XX Maintenance | construction | subject | 2024-06-03 | for the Interior | ー | ー | CC | XX Company | ー | ー | ⁠ |  |  | ±0D | AWS Lambda Seigenko exceeding the Lambda resource policy limit (20KB) | ■2024/09/17 BB It was discovered that XX company had not been implemented. Response required ----- ・ When XX (TT) added an event bridge, the resource policy limit was exceeded, so deployment is not possible. | ・Surveys ・Design ・CDK implementation ・ Test | 20 | [14 empty] | ー
3 | XXX Management | WBS converted ⇔ closed | XX Maintenance | ー | subject | 2024-04-01 | ー | ー | ー | BB | CC | ー | ー | middle |  | Only the NDRv of the retrofit design document remains. ※-2D | ±0D | XX Company Residual Tasks EvnetBrige→ Lambda → AWS Buck Lambda aggregation | ■2024/9/6 CC ND re-Rv was implemented on September 5. → points pointed out will be corrected, and internal re-RV will be implemented on September 9. ■2024/7/26 BB Completion of the retrofit design document. ⇒ internal Rv. NDRv Yet. ■2024/7/22 BB WBS converted |  | 15 | [14 empty] | ー
4 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-04-01 | ー |  |  | BB | DD | [6 empty] | XX Company Residual Tasks Network work shazan for external systems | ■2024/7/26 BB In order to respond as needed, votes will be raised on a case-by-case basis. ■2024/7/22 BB WBS Converted |  | 5 | [14 empty] | ー
5 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-04-01 | ー |  |  | BB | DD | [6 empty] | XX Company Residual Tasks Aurora StatisticsBackup MethodChange | ■2024/7/22 BB WBS-converted |  | 5 | [14 empty] | ー
6 | XXX Management | hold | XX Maintenance | ー | subject | 2024-04-01 | ー | ー | ー | BB | DD | ー | ー | low |  |  | ±0D | XX Company Residual Tasks Changing the CloudWatchLogs backup method | ■2024/7/22 BB The study is complete. Maintain the status quo for the time being. | ・Examination ・Design ・Manufacturing ・Exams | 20 | [14 empty] | ー
7 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-04-01 | ー |  |  | BB | All Zenin | ー | ー |  |  |  |  | Company XX Takeover | ■2024/7/26 BB Communicating with QA. ■2024/7/22 BB WBS Converted |  | 40 | [14 empty] | ー
8 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | Incident Response | 2024-06-12 | ー | ー | ー | BB | EE／FF／CC／GG | ー | 11324 | high |  | Once the delivery is completed. ※-2D | ±0D | Digital Testimony | ■2024/09/17 BB < Remaining Tasks> ・ Examination item document ■2024/8/1 EE There is an error in the KMS key reference in the production business container. → The security group of the endpoint on the production environment and △△ side was the default. (There is no problem with renovation and access) Correctly modify the endpoint in the production environment and ask the business to check the operation again. →, there was a chat message that "In the integrated test, we were able to successfully verify the signature data created by KMS in the production environment on the verification site." ■2024/7/26 BB Production-ready. 07/26It has been confirmed in business that there is no KMS connection problem from the container. 07/31~08/01 Digital certification test scheduled at Business TM. ■2024/7/22 BB Changed the handling of digital certificates from container-local to KMS. | < Requirements Definition> - Examination of mounting method ・Identification of the target < basic design > < Detailed Design > < Manufacturing (IT/Duplication (1)/Duplication (2)/Confirmation/Renovation/Production> < Procedure for Construction, Release, and Operation> <Unit test > < Bonding Test > < Comprehensive Exam> < Commercial Work Application > | 40 | [14 empty] | ー
9 | XXX Management | Close |  | ー | subject | 2024-06-12 | ー |  |  | BB | BB | ー | ー | Gao-kou |  |  |  | Insufficient DB User Privileges (XXDB) | ■2024/08/30 BB Handled by a common team ■2024/8/9 BB We are cooperating because we are organizing in a common team. ■2024/7/26 BB Temporary STOP due to priority of monitoring test ■2024/7/22 BB Since schema creation will be done in the future, additional permissions are required. Also, at this stage, it is only added to the table, but it is also required for the sequence. | - Authority organization - Creation of authorization procedures ・ Test item creation: | 10 | [14 empty] | ー
10 | XXX Management | Withdrawn | XX Maintenance | ー | subject | 2024-06-12 | ー |  |  | BB | BB | ー | ー | ⁠ |  |  |  | DB User Creation and Privilege Grant (Intermediate DB) | ■2024/09/17 BB Withdrawn due to implementation in the common process T. ■2024/7/26 BB DB user creation is performed in postgres user password change. Authority shall be examined and examined in conjunction with XXDB. ■2024/7/22 BB Intermediate DB also requires user creation and privilege granting. → PostgreSQL password is required. | * Excluding password change work - Procedure creation ・ Preparation of test items | 20 | [14 empty] | ー
11 | XXX Management | hold | XX Maintenance | ー | subject | 2024-06-12 | ー | ー | ー | BB |  | ー | ー | ⁠ |  |  | ±0D | DB User IAM Integration | ■2024/7/22 BB Since it is not implemented according to the basic design, it is necessary to take action. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・Test items ・ Operation procedure creation | 20 | [14 empty] | ー
12 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | subject | 2024-06-12 | ー | 2024-08-30 | ー | BB | CC | ー | ー | ⁠ |  | I want to release it at the end of August. Unadjusted | ±0D | Intermediate DBpostgres user password change | ■2024/10/08 BB Addition of new design documents to fill the shortage (not started) ■2024/09/17 BB Commercially ready ■2024/9/6 CC Scheduled to be applied to the production environment on September 9. ■2024/7/22 BB Change the postgres user password of the intermediate DB because it is unknown. * It is said that the intermediate DB does not use the postgres user, but verification is required. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・Test items ・ Operation procedure creation | 20 | [14 empty] | ー
13 | XXX Management | hold | XX Maintenance | ー | subject | 2024-06-12 | ー | ー | ー | BB |  | ー | ー | Low |  |  | ±0D | SecretManagerunnecessary definitionsdelete | ■2024/7/22 BB There is a high possibility that unnecessary settings remain in SecretManager. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・ Test items: | 20 | [14 empty] | ー
14 | XXX Management | Withdrawn |  | ー | subject | 2024-06-12 | ー |  |  | Hashimoto | ⁠ | ー | ー | Low |  |  |  | SSO Account Control | ■2024/7/22 Hashimoto SSO accounts need to be controlled because they can be connected from outside the commercial room. → need to be aware of GCAS linkage??? → decided to register an account only for NTTD users, so for the time being, there is no need to set it up for now. | ・Investigation and examination ・Detailed design - Writing construction procedures ・Test items ・ Operation procedure manual written by | 10 | [14 empty] | ー
15 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-06-12 | ー | ー | ー | BB | FF | ー | ー | Gao-kou |  |  | ±0D | Operational terminal access control | ■2024/7/23 BB It seems that the terminal can be authenticated by GCAS linkage. Receive correspondence time, manuals, etc.! ■2024/7/22 BB Since you can access other AWS environments from the operating terminal, It is necessary to be able to connect only to the production account from the production operation terminal, and only to the customer repair account from the test operation terminal. | ・Investigation and examination ・Detailed design - Writing construction procedures ・Test items ・ Operation procedure manual written by | 10 | [14 empty] | ー
16 | XXX Management | hold | XX Maintenance | ー | subject | 2024-06-12 | ー | ー | ー | BB |  | ー | ー | low |  |  | ±0D | Bastion Server (SkySea) Tera Macro Placement | ■2024/7/22 BB Tera Macro Arrangement (All Environments) | Macro Creation | 5 | [14 empty] | ー
17 | XXX Management | hold | XX Maintenance | ー | subject | 2024-06-12 | ー | ー | ー | BB |  | ー | ー | Low |  |  | ±0D | Request from Operational Tm Create a shared folder on the operational device | ■2024/7/22 BB File sharing between 3 test operating terminals, It will be possible to share files between three production terminals. * Do not use test operation terminals ⇔ production operation terminals! | ・Investigation and examination ・Detailed design - Writing construction procedures ・Test items ・ Operation procedure manual written by | 20 | [14 empty] | ー
18 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-06-12 | ー | 2024-08-30 | ー | BB | DD⇒GG | ー | ー | Gao-kou |  |  | ±0D | Group Connections Scheduling | ■2024/7/22 BB (1) Group connection test in the second and third periods, and confirmation of the actual connection date. (2) Confirmation of the connection method of the groupKiki | ・Confirmation and adjustment ・ Procedure writing | 15 | [14 empty] | ー
19 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-06-12 | ー |  |  | BB |  | ー | ー |  |  |  |  | Maintenance and Maintenance Review the operating procedure | [17 empty] | ー
20 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | CC | ー | ー | Low |  |  | ±0D | Request from Operational Tm Resource viewing procedure (container, DB, EC2 memory, CPU, disk IO?) ） | ■2024/7/22 BB Resource viewing procedure (container, DB, EC2 memory, CPU, disk IO?) ) | ・Resource Confirmation Procedure (RDS) ・Resource Confirmation Procedure (Container) ・Resource Confirmation Procedure (EC2) | 5 | [14 empty] | ー
21 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | II | ー | ー | Low |  |  | ±0D | Production setting pull-out (1) AWS | ■2024/09/17 BB This was carried out to obtain the IP, but it was found that there are differences in policy settings between production and modification, and there are services that do not work in production. ■2024/7/22 BB Retrieve the settings of the services used directly from the production environment. Create commands with the CLI. ・Relational Database Service ・Elastic Container Service ・EC2 Instances ・CloudWatch ・Route 53 ・Config ・VPC ・WorkSpaces ・Certificate Manager ・CloudTrail ・Managed Streaming for Apache Kafka ・Directory Service ・ElastiCache ・Network Firewall ・Security Hub ・QuickSight ・Elastic Load Balancing ・Inspector ・Key Management Service ・GuardDuty ・EC2 Container Registry (ECR) ・CodePipeline ・Backup ・Systems Manager ・Secrets Manager ・S3 ・SNS ・App Runner ・CodeBuild ・CodeCommit ・CodeArtifact ・Lambda ・Direct ConYY Company ・DynamoDB ・CloudWatch Events ・Elastic File System ・SQS ・Step Functions ・Glacier ・X-Ray ・WorkDocs ・Fault Injection Simulator ・Elastic File System ・WAF ・CloudFront ・Glue ・Migration Hub Refactor Spaces ・Service Catalog ・Location Service ・Service Catalog | ・ Procedure creation | 60 | [14 empty] | ー
22 | XXX Management | Withdrawn |  | ー | subject | 2024-07-16 | ー |  |  | BB | ⁠ | ー | ー | Gao-kou |  | Scheduled to be available in August: |  | Production setting pull-out (12) Pulling out the production cFn template | ■2024/09/17 BB Proceed in the CDK arrangement. ■2024/7/26 BB Scheduled to be available from 07/29~08/16. ■2024/7/22 BB Obtain the cFn template settings from the actual machine. Create commands with the CLI. | ・ Procedure creation | 5 | [14 empty] | ー
23 | XXX Management | Close |  | ー | subject | 2024-07-16 | ー | 2024-08-06 | ー | BB | BB | ー | ー | ⁠ |  |  |  | Overall Structure Diagram System Material Transfer Flow | ■2024/7/22 BB Creation of Composition Diagram | ・ Composition diagram written by | 5 | [14 empty] | ー
24 | XXX Management | Withdrawn | XX Maintenance | ー | subject | 2024-07-16 | ー |  |  | BB |  | ー | ー | ⁠ |  |  |  | Overall Structure Diagram System Deployment flow | ■2024/7/22 BB Creation of Composition Diagram | ・ Composition diagram written by | 5 | [14 empty] | ー
25 | XXX Management | Withdrawn | XX Maintenance | ー | subject | 2024-07-16 | ー |  |  | BB |  | ー | ー | ⁠ |  |  |  | Overall Structure Diagram System NW | ■2024/7/22 BB Creation of Composition Diagram | ・ Composition diagram written by | 5 | [14 empty] | ー
26 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-16 | ー | 2024-08-30 | ー | BB | CC | ー | ー | ⁠ |  | Work in progress Corresponding in the gap time | ±0D | Overall Structure Diagram System Surveillance | ■2024/7/22 BB Creation of Composition Diagram | ・ Composition diagram written by | 20 | [14 empty] | ー
27 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB |  | ー | ー | ⁠ |  |  | ±0D | Overall Structure Diagram System Other system linkage | ■2024/7/22 BB Creation of Composition Diagram | ・ Composition diagram written by | 5 | [14 empty] | ー
28 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB |  | AA | ー | ⁠ |  |  | ±0D | AA's request Confirmation of design ⇒ mounting omissions | ■2024/7/22 BB Monitoring implementation leakage occurred. Check if there are others. | ・ Survey and study | 20 | [14 empty] | ー
29 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | DD | ー | ー | Gao-kou |  | In parallel with the study, we are creating a mechanism for stopping at night for the time being. | ±0D | Cost Reduction (PCS Environment) EC2, RDS, and container nights and holidays | ■2024/9/17 BB The configuration will be changed to support holiday settings. ■2024/7/26 BB Scheduled to be examined on the realization method from 07/29~08/30. ■2024/7/22 BB Resource outages at night and on holidays * I was considering XX company, but is it okay to stop this at night and on holidays, and work and monitor? | ・ Survey examination Pull out with CLI! ・Detailed design - Writing construction procedures ・Test items ・ Writing of operation manual: | 30 | [14 empty] | ー
30 | XXX Management | WBS converted ⇔ closed | XX Maintenance | ー | subject | 2024-07-16 | ー |  |  | BB | CC | Performance Tm | ー | Gao-kou |  |  |  | Hint clause setting (XX information DB) | ■2024/09/17 BB The settings have already been supported, but there is a lack of design documents, so I will write a new one. (including intermediate DB) * Hint phrase, slow query (environment parameter system) ※Password ■2024/7/22 BB I'm only doing the real thing. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・Test items ・ Operation procedure creation | 15 | [14 empty] | ー
31 | XXX Management | WBS converted ⇔ closed | XX Maintenance | ー | subject | 2024-07-16 | ー |  |  | BB | CC | Performance Tm | ー | ⁠ |  |  |  | Hint clause setting (intermediate DB) | ■2024/09/17 BB Configurable. ■2024/7/22 BB I can't do it because I don't know the password of the postgres user. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・Test items ・ Operation procedure creation | 15 | [14 empty] | ー
32 | XXX Management | WBS converted ⇔ closed | XX Maintenance | ー | subject | 2024-07-16 | ー |  |  | BB | CC | Ms. NN | ー | ⁠ |  |  |  | Change postgres user password (intermediate DB) | ■2024/9/17 BB Responded ■2024/7/22 BB First of all, it is necessary to confirm whether it is okay to change the password of the PostgreSQL user. | ・Investigation and examination ・Detailed design ・CDK Design Document ・CDK implementation ・Test items ・ Operation procedure creation | 20 | [14 empty] | ー
33 | XXX Management | Close |  | ー | Work Request Received | 2024-07-16 | for customers | 2024-07-16 |  | BB | CC | ー | ー |  |  |  |  | Migration support Containers, Auora Resource Verification | ■2024/7/16 BB There is a request to check the status of containers, Auora CPU, and memory. | ー | 1 |  | BB | BB | 2024-07-16 | 2024-07-16 | BB | [8 empty] | ー
34 | XXX Management | Close |  | ー | Work Request Received | 2024-07-16 | for customers | 2024-07-16 |  | BB | CC | ー | ー |  |  |  |  | Migration support Auora Autovacuum, Auto-Analize Confirmation | ■2024/7/16 BB There is a request to confirm the date and time of Aurora's automatic vacuum and automatic Analize. | ー | 1 |  | BB | BB | 2024-07-16 | 2024-07-16 | BB | [8 empty] | ー
35 | XXX Management | Close |  | ー | subject | 2024-07-16 | ー |  |  | BB | CC | ー | ー |  |  |  |  | Migration support Retrieving the Execution Plan of Migration SQL | ■2024/7/22 BB YY's SQL has been received and corresponded. | Procedure Creation verification Production correspondence | 0.8 |  | BB | BB | 2024-07-16 | 2024-07-16 | BB | [8 empty] | ー
36 | XXX Management | Withdrawn |  | ー | subject | 2024-07-16 | ー |  |  | BB | CC | ー | ー | Gao-kou |  |  |  | Modification confirmation environment AWSBatch does not start | ■2024/7/22 BB ⇒07/18 There is a report that the Batch of the repair confirmation environment is not running partially. From the EventBrige side, Lambda is set as the target. From the Lambda side, as UU said, EventBrige is not set in the trigger. The target that has been deviated from the mystery is the one set in main3stack and is being investigated. I have been able to confirm that it works when I manually set the trigger from the Lambda side, but the setting is not reflected even if I run main3stack. By the way, other environments have a different document structure of CDK in the first place, so what about other environments? It's a state that can't be relied on. | ・Survey | 5 | [14 empty] | ー
37 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | CC | ー | ー | Gao-kou |  | Work in progress Scheduled to be available by the end of August: | ±0D | Make CDK PMWB management as soon as possible. | ■2024/7/22 BB Urgent! | ・Confirmation ・Stored ・ Document system diagram writing | 5 | [14 empty] | ー
38 | XXX Management | Close | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | CC | ー | ー | Gao-kou |  | Work in progress Scheduled to be available by the end of August: | ±0D | Make the document PMWB management as soon as possible. | ■2024/7/22 BB Urgent! | ・Confirmation ・Stored ・ Document system diagram writing | 5 | [14 empty] | ー
39 | XXX Management | Close |  | ー | subject | 2024-07-16 | ー |  |  | BB | BB | ー | ー | Low |  |  |  | Requests from the Common Team Review of DB Vacuum/Analyze Procedure Manual | ■2024/7/22 BB Somewhere in the week of 07/22. | ・ Reviewer correspondence | 0.1 |  | ■2024/7/23 BB Completion | BB | 2024-07-23 | 2024-07-23 | BB | [8 empty] | ー
40 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB | CC | HH | ー | Low |  |  | ±0D | Prevent SecretsManager passwords from peeking through the GUI | ■2024/7/22 BB Respond by changing policy settings. | ・Survey | 5 | [14 empty] | ー
41 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB |  | ー | ー | Low |  |  | ±0D | Redis slow log settings | ■2024/07/25 BB Since the Redis slow log is not output, set it to output. | - Surveys (settings, rotations, backups, monitoring) ・Design ・CDK implementation ・Tests ・Operational Procedures | 10 | [14 empty] | ー
42 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-16 | ー | ー | ー | BB |  | AA | ー | Low |  |  | ±0D | Auora Pricing Confirmation | ■2024/07/25 BB Creation of documentation that provides information on Aurora Provisioned and Aurora Serverless, caveats, and pricing. | ・Surveys | 5 | [14 empty] | ー
43 | XXX Management | Withdrawn | XX Maintenance | ー | Work Request Received | 2024-07-25 | ー |  |  | BB |  | Operational Tm | ー | Low |  |  |  | Request from Operational Tm Responding to insufficient specifications of operational terminals | ■2024/9/17 BB Supported by Operational Tm ■2024/07/25 BB Some of the operating terminals have low specs with 4GB of memory, so | ・Surveys ・Design ・ Support | 5 | [14 empty] | ー
44 | XXX Management | hold | XX Maintenance | ー | Work Request Received | 2024-07-25 | ー | ー | ー | BB |  | Operational Tm | ー | Low |  |  | ±0D | Request from Operational Tm Addition of bastion server | ■2024/9/17 BB It is necessary to confirm whether to purchase CAL or increase the number of bastion servers. ■2024/07/25 BB 08/06 It seems that the work will increase at the time of national liberation, so I would like to increase the number of connections. | appointment | 10 | [14 empty] | ー
45 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-25 | ー | ー | ー | BB |  | ー | ー | Low |  |  | ±0D | Is it okay to use the springboard server "SkySea Manager"? | ■2024/07/25 BB I am using the SkySea Messenger server as a stepping stone, but is it okay to use the manager server as a stepping stone? | appointment | 10 | [14 empty] | ー
46 | XXX Management | Withdrawn |  | ー | subject | 2024-07-25 | ー | 2024-08-06 |  | BB | BB | AA | ー | high |  |  |  | CDK Improvements | Withdrawn due to redundancy | - Organizing CDK document structure ・ Coordination of services | 15 | [14 empty] | ー
47 | XXX Management | Close |  | ー | subject | 2024-07-25 | ー | 2024-07-26 |  | BB | EE | AA | ー | ⁠ |  |  |  | Compare commercial room entry history and login history | ■2024/8/7 BB Since the entry history is in paper media, I want to digitize it. Make ⇒ a shared file. Create a CroudTrail log shaping tool? ■2024/7/26 BB Only CroudTrail log acquisition is completed. ■2024/7/25 BB AWS Manecon Login History by CroudTrail Logs Commercial Room Entry History SkySea Server Login History | Information Gathering Comparison confirmationJohou | 10 | [14 empty] | ー
48 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-07-25 | ー | 2024-07-26 | ー | BB | EE | ー | PMWB:11105 | Low |  | Supported DSM confirmation plan that seems to be a suspect part 2024/08/02 It is now possible to list keys with KMS connection in the Gabakura 3 environment (recovery cause unknown) → Inquiries to AWS for recovery are closed. It was decided to resume at the time of recurrence 2024/08/22 Check the suspect and the expected DeepSecurity URL filtering. * Prepare a procedure for checking the RUL filter to KMS. | ±0D | KMS service cannot be connected to the commercial room manager | ■2024/9/17 BB In Deep, URL filtering was not set, so it was found that it was not a suspicious place. It is necessary to check whether there is some kind of URL filtering on the VUTM side. ■2024/8/2 EE For some reason, the KMS connection to the Gabakura 3 environment now goes through. ・Inquiries to AWS will be CLOSED. ■2024/7/26 BB Influence of UNO's settings???? For the time being, I will contact AWS. |  | 5 | [14 empty] | ー
49 | XXX Management | Withdrawn |  | ー | Incident Response | 2024-07-25 | ー |  |  | BB |  | ー | PMWB:11073 | Gao-kou |  | Check the log retention period of the DSJ container (ct2215). The log retention period for each environment is as follows. IT environment 1 month Confirmation: 1 week Renovation 1 week Production 1 week |  | The log retention period of the DSJ container (intermediate SV) is less than one week(overlapping with No. 69). |  | investigation design manufacture test Release | 5 | [14 empty] | ー
50 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-07-25 | ー |  |  | BB |  | ー | PMWB:11101 | Gao-kou |  |  |  | Alert notification (ALARM: 'Cw002DqcvsSyntheticsFailed_error' in Asia Pacific (Tokyo)) | ■2024/9/17 BB At Company XX, an alert for the production work of the verification site. (External Monitoring) There is no answer as to what I did and why the alert was raised. | Survey | 5 | [14 empty] | ー
51 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-07-25 | ー | ー | ー | BB | CC | Operational Tm | PMWB:11020 | Gao-kou |  |  | ±0D | Job anomalies | 2024/9/4 Answered by AWS They replied that it would be executed immediately at the time of rerun. Answer to → Operation T 2024/9/3 Contacted AWS Support again. Substance*** We understand that AWS Batch does not support specifying the rerun (retry) interval. However, the upper limit of the number of reruns (retries) is a recognition that can be specified in the job definition. If a batch for which the number of reruns (retries) is set in AWS Batch terminates abnormally, is it correct to recognize that it will be re-executed immediately? ****** We received a response from AWS. Job re-execution will be carried out immediately. From here*** The job retry behavior in AWS Batch is implemented by setting the status of the target job to RUNNABLE, that is, returning it to the job queue once. After that, there is no guideline for how long it will take for the container to actually start due to job retries, as it depends on the amount of jobs in the job queue and the resource status of the computing environment So far*** Report as of [2024/7/22 14/15] byND platform Contacted AWS Support. Conclusion: It is caused by AWS, and it cannot be dealt with by the user. In the event of an event, it will be dealt with by rerunning as necessary. Regarding rerun in the event of a job failure, △△ recognizes that it is implemented in the following two patterns according to the business requirements (hearing results). (1) Rerun (2) Do not rerun, but execute on the following schedule. Since this job is designed not to be rerun as described in (2), please check whether it is executed without problems on the following schedule. *** ■ Answer Regarding the two questions we received, the message "Timeout waiting for network interface provisioning to complete." was caused by a temporary API issue on Fargate. Elastic Network Interface (ENI) This is an error that is displayed when provisioning is not completed within a certain time. [1] === Short description If Fargate is experiencing intermittent API issues on the underlying host, you might see the following error: - When the Fargate service attempts to attach an elastic network interface to the underlying infrastructure that performs tasks, you might see the following error message: Timeout waiting for network interface provisioning to complete (sic) Resolution (sic) Tasks that are manually launched using the RunTask API require manual retries. === Therefore, there is no means or settings that can be taken directly by the customer to avoid or resolve this event, and it is necessary to respond by retry when an event occurs. We apologize for any inconvenience caused by the problem on the AWS infrastructure side. Regarding this issue, AWS Batch provides a function [1] to automatically retry jobs that did not complete successfully. We would appreciate it if you could consider using this function according to your requirements. If there is anything that is lacking in the explanation, please do not hesitate to contact us. That's all for contact. Best regards. ■ References [1] Resolve network interface provisioning errors for Amazon ECS on Fargate ¦ AWS re:Post - xxxxrepost.aws/ja/knowledge-center/ecs-fargate-network-interface-errors [2] Automated job retries - xxxxdocs.aws.amazon.com/ja_jp/batch/latest/userguide/job_retries.html *** |  | 5 | 5 | [13 empty] | ー
52 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-07-25 | ー | 2024-07-31 |  | Hashimoto | Hashimoto | Sakai-san | ー | Gao-kou |  |  |  | Monitoring deficiency (Advanced Company bug) ★ Request for takeover received from Mr. Sakai | ■2024/7/26 Hashimoto 07/26~07/31AM. ■2024/7/25 Hashimoto [What cannot be detected] Alarm tuning for each service, response to implementation omissions -ECS: Fixed life-and-death monitoring settings. Make life-and-death monitoring according to the ⇒ account (obtain the necessary information from the account) ・EC2: Some EC2 process monitoring filter settings were missing, so added settings (SKY and Deep process monitoring added) ・Lambda: Implementation of lambda's own execution failure detection and notification -Aurora: Added settings because log monitoring filter settings were omitted. -Directory Service: Although it is a managed service, it adds life-and-death monitoring and log monitoring settings. ・AWS Backup: Added backup job status monitoring (backup failure detection and notification) [What to add a log] -Elasticache: Add log output settings only Hashimoto | Creation of environmental tests Digestive | 5 | [14 empty] | ー
53 | XXX Management | WBS converted ⇔ closed |  | ー | subject | 2024-07-25 | ー | 2024-08-02 |  | Hashimoto | Seto | Sakai-san | ー | Gao-kou |  |  |  | Auora intermediate db postgres user password lost | ■2024/9/17 Hashimoto Correspondence completed ■2024/9/6 Seto Scheduled to be applied to the production environment on September 9. ■2024/7/26 Hashimoto 07/26~08/09. ■2024/7/25 Hashimoto Intermediate DB Password Change, Hint Clause, Audit, User Creation | - Creation of intermediate DB_postgres password change procedure - Enable intermediate DBsharedPrelibraly ・Intermediate DB user creation | 5 | [14 empty] | ー
54 | XXX Management | New | XX Maintenance | ー | subject | 2024-07-25 | ー | 2024-08-02 | ー | BB | GG | ー | ー | low |  |  | ±0D | Get a VSIO license | ■2024/08/05 BB NTTD (company-wide) will not purchase licenses from FY25, and viso will be abolished. Some of the NW configuration diagrams are written in visio, so consider alternatives. | Design document rehash | 5 | [14 empty] | ー
55 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-29 | ー | ー | ー | GG | GG | ー | ー | Low |  |  | ±0D | NW Structure for Groups | ■2024/7/29 GG NW configuration between organization and XXX management *Supplement: BB There are four connection methods from the organization to XX management SYS, but the configuration is unknown, so |  | 10 | [14 empty] | ー
56 | XXX Management | Withdrawn |  | ー | subject | 2024-07-29 | ー | 2024-08-02 |  | BB |  | ー |  | Gao-kou |  |  |  | Verification backup correction due to failure on the site side | Responded by Company XX ■2024/7/30 BB Due to the change in the AppRunner path, it is necessary to modify the (list file) described in the backup script. No design documents. The script provided by XX is a Windows newline code, and there are many strange places. → in the process of hitting back. | [16 empty] | ー
57 | XXX Management | Close |  | ー | subject | 2024-07-31 | ー | ー |  | BB | BB／FF | ー | ？ | Gao-kou |  |  |  | CICD Deployment Errors | ■07/30 BB 2230, 2215 container deployment error investigation. → In the case of a new deployment on CodeBuild, the AP name should be created in advance, but the error occurred because it was not created. As a → foundation, it ends with a survey. | ー | ー | 0.5 | [13 empty] | ー
58 | XXX Management | hold | XX Maintenance | ー | subject | 2024-07-31 | ー | ー | ー | BB | BB | ー | ？ | Gao-kou |  |  | ±0D | Shell Management | ■2024/7/31 BB I received a script from XX for "backup correction due to failure on the verification site side", but I can't manage it because it seems that there is a script for each environment, such as CRLF even though it is a bash that runs on Linux. You have to manage it. | Examination of management method | 20 | [14 empty] | ー
59 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-07-31 | ー | ー | ー | BB | EE | ー | ？ | middle |  |  | ±0D | Pgpool 導入検討(PoC) | ■2024/10/08 BB Only the procedure to change the RDS endpoint settings of pgpool has not been done ■2024/8 BB WBS has been converted and is being supported. ■2024/07/31 BB It seems that there is a request to consider introducing pgpool. |  | 40 | [14 empty] | ー
60 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-07-31 | ー | ー | Business Tm (Company X) EE A1 Business Tm (XY Company) B1 | BB | EE | ー | 11167 | Gao-kou |  | Error accessing CT1101 container from Myna Portal Five incidents occurred at the following time. 2024-07-26 00:41 2024-07-26 03:28 2024-07-27 01:07 2024-07-27 04:06 2024-07-27 05:55 → said that there was no problem with the container at that time. | ±0D | Container ct1101 503 Gateway Error | ■2024/9/5 EE Comment from NTTD It's been a while since the inquiry, and the original inquiry was received by Digi Agency ACTeams, and it has not been answered. No questions asked. Since it is closed on the AC side, this case will also be closed 2024/9/4 Answer (additional information) requested by AWS. Information is being requested from Operation and Maintenance T. 2024/9/3 Contacted AWS Support again. Substance*** We have received a notification from another system that a "503 Gateway Error" has been returned when accessing the CT1101 container of this system. It is said that it occurs during the following time period, but the error has not occurred on this system side (container). Therefore, please let us check if there was a problem at the time on the AWS side. There were 5 Gateway errors in the following time. 2024-07-26 00:41 2024-07-26 03:28 2024-07-27 01:07 2024-07-27 04:06 2024-07-27 05:55 a.m****** ■2024/08/05 BB Since it is an online application function, it will be a CT1101 container. The first answer was that there was no blockage in the XXX management at that time, and there was no error on the XXX management side. (Confirmed by TDC) The AC replied that it was presumed to be a temporary event because it did not occur outside of the relevant time, but we believe that the cause should be confirmed as the XXX management side just in case. ▼ Matters to be confirmed It is said that a 503 Gateway error is returned at the following time / function, so please check the cause. ・Time of occurrence 2024-07-26 00:41:29 ～ 2024-07-26 03:28:25 2024-07-27 01:07:11 ～ 2024-07-27 05:55:54 ・Function name ○○○○○○IF --- There were 5 Gateway errors in the following time. 2024-07-26 00:41 2024-07-26 03:28 2024-07-27 01:07 2024-07-27 04:06 2024-07-27 05:55 | Survey | 10 | [14 empty] | ー
61 | XXX Management | hold | XX Maintenance | ー | subject | 2024-08-02 | ー | ー | ー | BB |  | ー | ？ | Low |  |  | ±0D | XX Company Bug Metric statistics have become "average" | ■2024/08/05 BB Some of the metric statistics are "average", so it takes time for an alert to be issued. →XX Bug | investigation design manufacture test Release | 15 | [14 empty] | ー
62 | XXX Management | hold | XX Maintenance | ー | subject | 2024-08-02 | ー | ー | ー | BB |  | ー | ？ | middle |  |  | ±0D | XX Company Bug There is no monitoring on the Osaka region side at all. | ■2024/08/05 BB According to XX, "the Osaka region is for backup purposes", so it is unnecessary, but it is necessary to confirm whether it is really okay without monitoring. | investigation design manufacture test Release | 15 | [14 empty] | ー
63 | XXX Management | Close | XX Maintenance | ー | subject | 2024-08-02 | ー | ー | ー | BB |  | ー | ？ | middle |  |  | ±0D | XX Company Bug Inadequate account management books | ■2024/9/17 BB When you're done, close it. ■2024/08/05 BB The user/password listed in the account book is incorrect. → there is a high possibility that others are also wrong, so I am having it checked by XX company. ＊＊＊＊＊ [08/02 18:12] PS3 Kobayashi, Kengo (NTT DATA) Hashimoto, Hayato (NTT DATA) I'm sorry about the account management book It's difficult today, but I'll check it again by the beginning of next week and try to post accurate information. Once the login information is as follows admin@nqs-stg.local hf-+4Eh4%yp+NrJM like 1 | Survey | 5 | [14 empty] | ー
64 | XXX Management | New | XX Maintenance | ー | subject | 2024-08-05 | for the Interior | ー | ー | EE |  | ー | ？ | Low |  |  | ±0D | About running CloudHSM in an ST replication (1) environment | ■2024/8/5 EE About CloudHSM operation (cost) After creating keys and CSR, only key storage and backup are required, and the cost of operation is enormous. You can reduce costs by deleting the HSM once and recovering from the backup if you need to create a key. xxxxrepost.aws/en/knowledge-center/ | investigation design manufacture test Release | 15 | [14 empty] | ー
65 | XXX Management | Close |  | ー | task | 2024-08-06 | ー | ー | ー | BB | CC | ー | ？ | middle |  |  |  | for the acquisition of national liberation resources Kokumin | ■2024/8/10 Correspondence completed ■2024/8/6 01. Server Usage →CPU, memory, and disk usage of each server (EC2, on-premise) 02. Network Usage → Network Traffic 03. Container Usage → container CPU, memory, and file system usage 04.DB Usage → Aurora CPU, Memory, Number of Connections, Storage Capacity → DynamoDB Capacity Unit Consumption Rate, Throttling 05. Lambda Usage Number of → processes 06. Online Processing Status → Online Response Time 07. Batch processing status → Batch Response Time 08. User Usage → Number of XX registrants (number of registrants of XX holders such as doctors and nurses) Number of → Participating Organizations 09. External Cooperation Number of API executions for → linkage systems (e.g., Juki Net) 10. AWS Usage Fee → AWS usage fee (monthly) |  | 0.5 | 0.5 | [13 empty] | ー
66 | XXX Management | Withdrawn | XX Maintenance | ー | task | 2024-08-06 | ー | ー | ー | BB |  | ー | ？ | middle |  |  | ±0D | National Liberation Resource Acquisition Procedure | ■2024/8/6 BB Control? I was given only the lineup that I wanted to get monthly resources from, but there is no procedure. The batch response time is described in the capacity management table as "measured from the application log", but there is no such procedure. | investigation design manufacture test Procedure Writing Release | 20 | [14 empty] | ー
67 | XXX Management | Close |  | ー | Incident Response | 2024-08-06 | ー | 2024-08-06 | ー | BB | FF | ー | 11463 11072 | Gao-kou |  |  |  | Log Monitoring Alert: Container Restart | ■2024/8/6 BB ----------------------------------------------------- When I checked with the intermediate SV members of the public fund project, there is information that rolling updates due to AWS Fargate maintenance occur several times a month. It was speculated that this was the cause because it was a time when other processes did not work. ・ AWS Fargate maintenance is notified in advance by AWS. ・The frequency of occurrence is about several times a month. | [16 empty] | ー
68 | XXX Management | New | XX Maintenance | ー | Incident Response | 2024-08-06 | ー | ー | ー | BB |  | ー | 11463 11072 | middle |  |  | ±0D | is no notification setting for the maintenance health dashboard. | ■2024/9/17 BB It has already been dealt with by XX company, but it is necessary to scrutinize it because all maintenance information has come to be flown in. ■2024/8/6 BB AWS maintenance notifications are not set. |  | 20 | [14 empty] | ー
69 | XXX Management | Close |  | ー | Incident Response | 2024-08-06 | ー |  |  | BB | BB | ー | 11073 | ⁠ |  | 2024/8/22 Check the log retention period of the DSJ container (ct2215) (obtain evidence). 3 months in the design document *** IT environment 1 month Confirmation: 1 week Renovation 1 week 2024/8/26 Production: 1 week: | When I asked XX if they had changed the log retention period before, they replied that it was corrected to one week around the end of May and has not been changed since then. It is also listed in PMWB. PMWB has been closed on the same day by SS. | The log retention period of the DSJ container (intermediate SV) is less than one week(overlapping with No. 49). | ■2024/9/6 When I asked XX if they had changed the log retention period before, they replied that it was corrected to one week around the end of May and has not been changed since then. It is also listed in PMWB. PMWB has been closed by OO on the same day. ■2024/8/6 BB Incident: Detected during log investigation of 11018. The logs of the DSJ container (ct2215) are only stored up to the logs of 3 days ago. Since the transmission and reception logs of telegrams (status monitoring) for 51 agencies continue to appear, the log capacity has been rotated largely. |  | 5 | 3 man-day |  | GG | 2024-09-03 | [10 empty] | ー
70 | XXX Management | hold | XX Maintenance | ー | subject | 2024-08-07 | ー | ー | ー | BB |  | ー | ー | ⁠ |  |  | ±0D | Check your security score Security Hub | ■2024/08/07 BB ★ What is going on with AWS services from a security perspective? |  | 3 | [14 empty] | ー
71 | XXX Management | hold | XX Maintenance | ー | subject | 2024-08-07 | ー | ー | ー | BB |  | ー | ー | ⁠ |  |  | ±0D | Cost Analysis Cost Intelligence Dashboard | ■2024/08/07 BB ★ Cost analysis is like AWS. |  | 3 | [14 empty] | ー
72 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | subject | 2024-08-07 | ー | ー | ー | BB |  | ー | ー | ⁠ |  |  | ±0D | Verification site: The S3 path has been changed in the CDK deployment. | ■2024/9/17 BB There is a considerable difference between before and after the correction. Since the setting to output to → CloudWatchLogs is not specified, a log group is created every time it is flushed. In addition, since the monitoring setting is stack, it is necessary to modify the monitoring setting stack as well. ■2024/08/07 BB ★When I rebuilt Apprunner, the S3 path changed. To get the CDK before and after. |  | 3 | [14 empty] | ー
73 | XXX Management | Close |  | ー | Incident Response | 2024/08/08 | ー |  | Pro Tube Tm C1 Kang | BB | BB | ー | 11524 | ⁠ |  |  |  | 【NQS】Log Monitoring Alert Notification | ◆Time: 2024-08-08 10:15:24 ◆Metric Filter Name: Cl006OpmSysApplication_011_1_WARN_KC5W ◆Alarm Name: Cw002OpmSysApplication_011_1_WARN_KC5W ◆Log Group: Cl006OpmSysApplication_011_1 ◆Host Name: A85030011 ◆Log Content: <Event ...> ... <RenderingInfo Culture='en-US'> <Message>KCCM028W Failed to establish connection. </Message> <Level>Warning</Level> <Task></Task> <Opcode>Information</Opcode> <Channel></Channel> <Provider></Provider> <Keywords> <Keyword>Classic</Keyword> </Keywords> </RenderingInfo> </Event> | Survey | 0.5 |  | "Host name: A85030011" is an information provision server on the account premises, so it has been dispatched to the YY platform. | [12 empty] | ー
74 | XXX Management | Close |  | ー | Incident Response | 2024/08/08 | ー |  | Pro Tube Tm C1 Kang | BB | BB | ー | 11525 | ⁠ |  |  |  | 【NQS】Log Monitoring Alert Notification | ◆Time: 2024-08-08 10:15:53 ◆Metric Filter Name: Cl006OpmSysSystem_011_ERR ◆Alarm Name: Cw002OpmSysSystem_011_ERR ◆Log Group: Cl006OpmSysSystem_011 ◆Host Name: A85030011 ◆Log Content: <Event ...> ... <RenderingInfo Culture='en-US'> <Message>JKCAPTXM0002 service was terminated due to an unexpected cause. This is the first forced termination of this service.</Message> <Level>Error</Level> <Task></Task> <Opcode></Opcode> <Channel></Channel> <Provider>Microsoft-Windows-Service Control Manager</Provider> <Keywords> <Keyword>Classic</Keyword> </Keywords> </RenderingInfo> </Event> | Survey | 0.5 |  | "Host name: A85030011" is an information provision server on the account premises, so it has been dispatched to the YY platform. | [12 empty] | ー
75 | XXX Management | Close |  | ー | Incident Response | 2024/08/08 | ー |  | Pro Tube Tm C1 Kang | BB | BB | ー | 11526 | ⁠ |  |  |  | 【ZNTM-XX】Failed to send code request file from information server to J-LIS | ◆Time:2024-08-08 10:20:03 ◆ Metric filter name: OpmSendServiceMonitoring_011 ◆ Alarm name: Cw002OpmSendServiceMonitoring_011 ◆ Log group: Cl006OpmSendServiceMonitoring_011 ◆ Hostname: A85030011 ◆ Log contents: 2024/08/08 10:15:23,Failed to send ,31,202408070702408070000000229 ,28,JZCGFA85030001080800004Y.dat , 739, ,N51000002,0000001 | Survey | 0.5 |  | "Host name: A85030011" is an information provision server on the account premises, so it has been dispatched to the YY platform. | [12 empty] | ー
76 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024-08-09 | ー | ー | Operation Tm: ZZ RR Eun | BB | CC | ー | ー | ⁠ |  |  | ±0D | There is no procedure for obtaining resources for regular work. | ■2024/8/9 BB I don't think the operation team can create the procedure, so I need to create it on the foundation. |  | 10 | [14 empty] | ー
77 | XXX Management | Close |  | ー | Task (work request received) | 2024-08-21 | ー | 2024-08-23 | Operation Tm: XZ D1 | BB | CC | ー | ー | ⁠ |  |  |  | July Capacity Monitoring Survey Request | ■2024/08/21 BB Details of the request **** For details, please refer to Teams. (1) DB usage >number of Aurora > connections (see near line 924 of Excel below) Looking at the graph of 7/1~7/31, it seems that there are regular spikes, so investigate the following ・ When is the peak day? ・ When are the peak hours? ・ There may be spikes on the container side, so check it together and identify the container (if possible) (2) Lambda usage > number of launches (see near line 1199 of Excel below) There is a spike on 7/24. The maximum number of lambdas is 1000, but check how many were there. |  | 5 | [14 empty] | ー
78 | XXX Management | Close | XX Maintenance | ー | Task (work request received) | 2024-08-21 | ー | 2024-09-06 | YY Company | BB | BB |  | ー | high |  | 2024/8/22 Confirmation of the monitoring method for operational terminals and network devices |  | Daimon Power Outage Response Survey | ■2024/9/17 BB Regarding monitoring alerts, the policy is to ignore them, so there is no special response. ■2024/9/6 The status of the agent is monitored by Trend Micro Deep Security (Manager). Assume the following notification on the terminal Power OFF → Power ON ****** Trend Micro Deep Security Event List P212 in the Administrator's Guide Event ID: 730 Severity: Error Event: Offline Note: The manager is unable to communicate with the computer. This does not mean that agent/appliance protection is disabled. For details, see Computer and Agent/Appliance Status. Event ID: 731 Severity: Information Event: Back Online Remarks: (There are no remarks.) *** ■2024/08/21 BB Operational terminals will be shut down due to a planned power outage at the Daimon operation base, but it is necessary to confirm whether monitoring and deterrence can be performed. |  | 5 | [14 empty] | ー
79 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-21 | ー | 2024-08-30 | Operation Tm: OO | BB | BB | ー | 11687 | high |  | 2024/8/22 [Event] HTTP Status 504 Gateway Timeout Error When Communicating from CT3106 to xxxx 2024/08/21 19:42 Alarm every 5 minutes after <> 2024/08/21 19:47 2024/08/21 19:52 2024/08/21 19:57 2024/08/21 20:02 2024/08/21 20:07 2024/08/21 20:12 2024/08/21 20:17 2024/08/21 20:22 2024/08/21 20:27 2024/08/21 20:32 2024/08/21 20:37 2024/08/21 20:42 2024/08/21 20:47 2024/08/21 20:52 2024/08/21 20:57 2024/08/21 21:02 <Last > [Cause] It is said that the service down occurred due to the LB failure on the KOKOPAS side. (19:39 failure - 21:03 recovery) (The time zone of the alarm occurrence is also the time of failure on the KOKOPAS side - recovery time) |  | KOKOPAS communication error | ■2024/08/27 BB Answered to Business Tm Can you analyze where the 504 error is being returned from in the > platform T? > whether it is returned from xxxx or within the network within △△? At the time of the ⇒504 error, it is connected to xxxx, so it is judged that it is not on the △△ side. The only way to confirm whether it is the ALB of xxxx or the server is to contact the xxxx side. ■2024/08/26 BB There is a notification of LB failure on the xxxx side. < Impact on operations> If a citizen has made a payment during this time period, the payment completion information cannot be linked from xxxx, and the payment status in △△ is not completed. From the point of view of the public, it looks like they are waiting for status settlement on the Myna Portal, even though they should have made a payment. From the organization's point of view, the payment has not been completed, so the examination cannot be started. During the time period when the error occurred, it was confirmed that there were no applications with a settlement status waiting for settlement, so the above effects were not affected ■2024/08/21 BB HTTP status 504 Gateway Timeout is returned when communicating from CT3106 to xxxx from 19:42. I would like to see where the 504 error is being returned from. xxxx is checked for failure from the operation Tm. |  | 3 | [14 empty] | ー
80 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Task (work request received) | 2024-08-22 | ー | 2024-08-23 | YY XZ Sha | BB | GG | ー | ー | high |  | 8/27 Correspondence completed 2024/8/22 [Situation] We are investigating the registration details of JobNet. I plan to consult with Mr. Ito tomorrow afternoon. |  | Batch addition request response (IT environment) | ■2024/08/27 GG Completed 2 batches of adding to the IT environment. The schedule for other environments is as follows Replication (1) Applied by 9/13 (9/17 ~ 2nd period ST) Duplicate (2) Applied by 9/13 (9/17~ 2nd stage performance) Connection check applied by 9/20 (9/24 ~ 2nd term linkage) Modification confirmation Not applied for a while to synchronize with commercial (end of October?) Production Released at the end of October ■2024/08/22 BB They want you to add 2 batches to the IT environment. Schedules for other environments need to be confirmed!! |  | 10 | 5 | ■2024/08/27 GG Completion. | BB | 2024-08-27 | [10 empty] | ー
81 | XXX Management | Supported by | XX Maintenance | ー | subject | 2024-08-23 | ー | 2024-08-30 | ー | BB | FF |  | ー | middle |  |  |  | Jump Account Access Control | ■2024/08/23 BB Implemented. No design document. |  | 15 | [14 empty] | ー
82 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | BB |  | 11743 | middle |  |  |  | AWS Notification Message(HealthEvent) | ■2024/08/26 BB There is maintenance at Direct ConYY (Equinix TY2) and the connection is broken. Subject to dxvif-fhb1koep (GSS Direct ConYY connection) There is no problem because it is redundant and a standby line. Answer from GSS***** In the AWS Direct ConYY (AWS closed connection service) used in the GSS Government Cloud Connection Service AWS has informed us that maintenance work will be required on the line you are using for your system, so we will inform you as follows. 【Schedule】 Tuesday, August 27, 2024 1:00 a.m. ~ 5:00 a.m. Planned maintenance by AWS at the connection point of TYO4 (Equinix TY2, Tokyo, Japan) [Communication impact] without * During the maintenance period, related AWS Direct ConYY services may not be available. Since TYO4 (Equinix TY2, Tokyo, Japan) is a standby line, there is basically no communication impact on the GSS government cloud connection you are using. 【Notes】 Depending on the AWS monitoring settings on the Government Cloud, anomalies may be detected. Please be silent about errors related to GSS Government Cloud Connection (TYO4) during the relevant work hours. That's it. Thank you. The following is an excerpt from the message***** <resources> dxvif-fhb1koep <service> DIRECTCONYY T <eventTypeCode> AWS_DIRECTCONYY company T_MAINTENANCE_SCHEDULED <eventTypeCategory> scheduledChange <eventScopeCode> ACCOUNT_SPECIFIC <latestDescription> Planned maintenance has been scheduled on an AWS Direct ConYYt endpoint in Equinix TY2, Tokyo, Japan. During this maintenance window, Your AWS Direct ConYY services associated with this event may become unavailable. This maintenance is scheduled to avoid disrupting redundant conYY at the same time. If you encounter any problems with your conYY after the end of this maintenance window, please contact AWS Support(1). (1) xxxxaws.amazon.com/support |  | 0.5 | 0.5 | [13 empty] | ー
83 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | BB |  | 11744 | middle |  |  |  | AWS Notification Message(HealthEvent) | ■2024/08/26 BB DIRECTCONYY社Tのメンテナンス完了通知のため問題なし。 ＊＊＊＊＊以下メッセージ抜粋＊＊＊＊＊ <resources> dxvif-fgzr8pzd <service> DIRECTCONYY社T <eventTypeCode> AWS_DIRECTCONYY社T_MAINTENANCE_COMPLETE <eventTypeCategory> accountNotification <eventScopeCode> ACCOUNT_SPECIFIC <latestDescription> We would like to inform you that the maintenance for AWS Direct ConYY社t endpoint in Equinix TY2, Tokyo, Japan from Fri, 23 Aug 2024 17:00:00 GMT to Fri, 23 Aug 2024 21:00:00 GMT has been completed. Please find your AWS Direct ConYY社t services that would have been affected by this maintenance in the \\\"Affected Resources\\\" tab of your AWS Health Dashboard. If you have any questions regarding the completed work, or if you would like to report a fault or adjust your contact information, please contact AWS support at xxxxaws.amazon.com/support . |  | 0.5 | 0.5 | [13 empty] | ー
84 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | BB |  | 11746 | middle |  |  |  | DB connection timed out (terminating connection due to idle-in-transaction timeout) | ■2024/08/27 BB After connecting to the "postgres" database with the "psm401zmpr01" user This is a message that the connection was terminated because it was idle for a long time during the transaction (no action was taken). The main reason for this error is that a termination operation such as COMMIT or ROLLBACK does not occur after the transaction has started. This is the case if it has been left for a long time. 10.170.37.220 is a connection from a container in the "AZ:ap-northeast-1c business container subnet", so As a business container, please check whether COMMIT and ROLLBACK are properly coded in the process of connecting to the DB. |  | 5 | [14 empty] | ー
85 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | BB |  | 11747 | middle |  |  |  | DB connection timed out (terminating connection due to idle-in-transaction timeout) | ■2024/08/27 BB After connecting to the "postgres" database with the "psm401zmpr01" user This is a message that the connection was terminated because it was idle for a long time during the transaction (no action was taken). The main reason for this error is that a termination operation such as COMMIT or ROLLBACK does not occur after the transaction has started. This is the case if it has been left for a long time. 10.170.34.179 is a connection from a container in the "AZ:ap-northeast-1a business container subnet". As a business container, please check whether COMMIT and ROLLBACK are properly coded in the process of connecting to the DB. |  | 5 | [14 empty] | ー
86 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | GG |  | 11741 11775 | middle |  |  |  | IFS WebAp server fails to send message error |  |  | 5 | [14 empty] | ー
87 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | EE |  | 11161 11742 11774 | middle |  |  |  | 【NQS】Log Monitoring Alert Notification |  |  | 5 | [14 empty] | ー
88 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-08-30 | ー | BB | DD |  | 11745 11482 11651 | middle |  |  |  | Error messages related to digital certificate verification Verification Site WAF Exclusion Settings |  |  | 5 | [14 empty] | ー
89 | XXX Management | Withdrawn | XX Maintenance | ー | Incident Response | 2024-08-26 |  | ー | ー | BB |  |  | - | high |  |  |  | Schedule for the Distribution of Infrastructure Communication Test and Secret Communication Test and Secret Communication Certificate for the Transition of the Third NWS Renewal | NN is responding |  | 10 | [14 empty] | ー
90 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Incident Response | 2024-08-26 |  | 2024-09-20 | ー | BB | BB |  | 11780 | middle |  |  |  | AWS Health Maintenance Notifications | ■2024/08/27 BB A notification from the AWS Health Dashboard will result in a rolling update of the listed container, stopping the task and replacing it with a newer version. At that time, a life-alive monitoring alert (Cw002ECS-LOG-ALIVE-prd-ctXXXX-xxxxxx-xxxxx) will be issued. → closed because there is no impact on business. Start time: September 3, 2024 03:00 (GMT) End time: September 10, 2024 03:00 GMT |  | 1 | 1 | [13 empty] | ー
91 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | Incident Response | 2024-08-27 |  | ー | ー | BB | CC |  | - | middle |  |  |  | [Company XX: Work omission] Operation procedure (resource acquisition) | ■2024/08/27 BB Create a procedure for resource acquisition! |  | 5 | [14 empty] | ー
92 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024/08/27 |  | ー | ー | BB |  |  | 11776 | middle |  | - |  | NWS Linked Correspondence Error 2024-08-26 20:13:39 | [17 empty] | ー
93 | XXX Management | Withdrawn |  | ー | Incident Response | 2024/08/27 |  |  | ー | BB | YZ Sha |  | 11199 | middle |  | - |  | Internal: An error occurs in CICDpipeline during the production release of the intermediate server. | [17 empty] | ー
94 | XXX Management | Withdrawn | improvement | ー | Incident Response | 2024/08/27 |  | ー | ー | BB | XX Company |  | 11056 | middle |  | - |  | 【ZNTM-24】 【Work Request】 Request for Penetration Test (Verification Site Drilling) | [17 empty] | ー
95 | XXX Management | Supported by | XX Maintenance | ー | Incident Response | 2024/08/27 |  | ー | ー | BB | JJ⇒BB |  | 11018 12886 | high |  | - |  | [XX Company Bug] 【ZNTM-20】 Alert detection by IFS operation monitoring (detected on the NWS side) | The timeout setting seems to be wrong. ＊＊＊＊＊＊＊＊＊＊＊＊＊＊＊＊ [Events that occurred] An OutOfMemory error occurred in the DSJ container of the intermediate server. The container was stopped and could not receive telegrams during that time. [Cause of occurrence] This is due to the fact that the container was stopped due to bug 10309 due to the response to Incident 10822 (IFS resident batch start) performed on 7/19 (Friday). Incident 10822:xxxxpmwbv-portalv002.almcloud.nttdata.com/ads/7070wxRaby/gcms/_workitems/edit/10822 Bug 10309:xxxxpmwbv-portalv002.almcloud.nttdata.com/ads/7070wxRaby/gcms/_workitems/edit/10309/ [Business impact] No impact on business (it has been confirmed that code acquisition and information inquiries have not been made) | [16 empty] | ー
96 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | Incident Response | 2024/08/27 |  | 2024-10-31 | ー | BB | CC |  | 10813 | middle |  | - |  | [XX Company Bug] Deep Security Unwanted Alert Scrutiny | [17 empty] | ー
97 | XXX Management | Supported by | XX Maintenance | ー | task | 2024/08/27 |  | 2024/ | ー | BB |  |  | ー | middle |  | - |  | GCAS support | I want to identify tasks. \\ecom-fs\general folder019\FY2024\~ | [16 empty] | ー
98 | XXX Management | WBS conversion ⇔ now supported | improvement | ー | task | 2024/08/27 |  | ー | ー | BB | DD |  | ー | middle |  | - |  | Addition of 2nd batch of work | [17 empty] | ー
99 | XXX Management | Withdrawn | XX Maintenance | ー | subject | 2024/08/27 |  | ー | ー | BB |  |  | ー | middle |  | - |  | 【XX社バグ】sns unsubscribe対応 | Set so that "SNS unsubscribe" is not performed even if the link is pressed. | [16 empty] | ー
100 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | subject | 2024/08/27 |  | ー | ー | BB | JJ⇒BB |  | ー | middle |  | - |  | 【XX社バグ】sns unsubscribe確認対応 | ■2024/9/17 BB Create a new subscription so that it is not unsubscribed when you click the link. Because you pressed it? I asked you to check if it was canceled. | [16 empty] | ー
101 | XXX Management | Close | XX Maintenance | ー | task | 2024/08/27 |  | 2024-08-30 | ー | BB | BB/GG/EE |  | ー | middle |  | - |  | Audit Readiness | Fill out the security hearing sheet. \\ecom-fs\general folder019\FY2024\~ ∟xxxxx.xlsm | [16 empty] | ー
102 | XXX Management | Close | XX Maintenance | ー | Task (work request received) | 2024-09-04 |  | 2024-09-05 | ー | GG | GG | Ms. D1 | ー | middle |  |  |  | Canceling the AWS Resource Stop Script for Cloned Environments ➁ | 9/9 9/9 (Mon) ~ 9/13 (Fri) There is a request to extend the cancellation period of the stop script. Changed activation timing ⇒ "9/9" to "9/17" 9/5 Disable AWS resource stop script in replication environment ➁ Tomorrow, 9/5 (Thursday) ~ 9/8 (Sunday), can you cancel the AWS resource stop script of the replication environment ➁? There is no problem if the replication environment ➁ can be used after 19:00 tomorrow 9/5 (Thursday), so please respond by 16:00 tomorrow 9/5 (Thursday). We would appreciate it if you could contact us when the response is completed. Activation should be carried out on 9/9! | [16 empty] | ー
103 | XXX Management | Waiting for Completion Approval | XX Maintenance | ー | Task (work request received) | 2024-09-04 |  | 2024-09-05 | ー | GG／EE | GG/EE | KK |  | middle |  |  |  | Confirmation of answers to the Personal Information Protection Voluntary Inspection Check Sheet | 9/5 Operational terminals, test operating terminals and SkySea's patch status and reported to KK. - Checking and applying the patch application status of SKYSEA - Checking and applying Windows definition files Implementation of work. | [16 empty] | ー
104 | XXX Management | Close | XX Maintenance | ー | subject | 2024-09-06 |  | ー | ー | BB | Ms. NN | E1 |  | Gao-kou |  |  |  | Inquiries from NWS 3rd term | ■2024/9/17 BB It is assumed that it is not a conscious process. Does it take GSS wrapping into account? | [16 empty] | ー
105 | XXX Management | WBS conversion ⇔ now supported | improvement | ー | task | 2024-09-06 |  | ー | ー | BB | CC | Ms. LL |  | Gao-kou |  |  |  | Security Diagnosis Response | ■2024/9/17 BB Since there are no logs, procedures, or evidence that was implemented in the first period, it is necessary to set up from scratch. | [16 empty] | ー
106 | XXX Management | Close | XX Maintenance | ー | Inquiry Received | 2024-09-06 |  | ー | ー | BB | FF | F1 |  | Gao-kou |  |  |  | Inquiries from Digi Agency | From Digi Agency In the case of a GSS network or LGWAN connection method, what is the IP address associated with the FQDN? Currently, when resolving the name with the DNS on the LGWAN side, the FQDN of both the production environment and the connection check environment returns 210.143.9.47. However, the document you provided states that it is 118.107.155.50 (GSS network GIP). Since the My Number network refers to a dedicated DNS that is different from the GSS network and LGWAN, it is necessary to set it individually. Please let me know. | [16 empty] | ー
107 | XXX Management | WBS conversion ⇔ now supported | XX Maintenance | ー | Incident Response | 2024-09-09 |  | ー | ー | BB | JJ |  | 12761 | high |  |  |  | SocketTimeout (My Napo Declaration) | [17 empty] | ー
108 | XXX Management | Close | XX Maintenance | ー | Incident Response | 2024-09-09 |  | ー | ー | BB | JJ |  | 12710 | high |  |  |  | LB Log Survey Request | Check "Lb104a1003" from "10.170.20.94" to log output | [16 empty] | ー
109 | XXX Management | hold | XX Maintenance | ー | subject | 2024/09/13 |  | ー | ー | BB |  |  | ー | middle |  |  |  | Monitoring definition is incorrect for non-production | ■2024/9/17 BB EventBrigeRule(Cw003Batchjobtimeout) is incorrect for non-production → the name is different or the settings are different. | [16 empty] | ー
110 | XXX Management | Close | improvement | ー | subject | 2024/09/13 |  | ー | ー | BB |  |  | ー | middle |  |  |  | About the 2nd Term Reliability Test | ■2024/10/08 BB The second base ST is closed due to no support. ■2024/09/17 BB I have been contacted by "??" asking if the reliability test is scheduled on the platform, but I recognize that it is unnecessary because there are only two business batches to be added on the platform in the first place. No answers. | [16 empty] | ー
111 | XXX Management | Withdrawn | improvement | ー | subject | 2024-09-19 |  | ー | ー | BB |  | business | [5 empty] | Changing the time of an existing job * 2nd release request | ■2024/10/08 BB Company XX has responded. ■2024/9/20 BB It seems that this is a request from Business T, but I don't recognize it. | [16 empty] | ー
112 | XXX Management | WBS conversion ⇔ now supported | improvement | ー | subject | 2024-09-19 |  | ー | ー | BB | CC | YY Company | [5 empty] | Add monitoring settings * 2nd release request | [17 empty] | ー
113 | XXX Management | WBS conversion ⇔ now supported | improvement | ー | subject | 2024-09-19 |  | ー | ー | BB | EE／GG | Business management? | [5 empty] | Request for Preparation of Release Procedure *2nd term | [17 empty] | ー
114 | XXX Management | Waiting for Completion Approval | improvement | ー | subject | 2024-09-19 |  | ー | ー | BB | GG | application | 12979 12980 |  |  |  | 2024/9/20 PMWB Updated | C1WS Alert | ■2024/10/08 BB There is no problem because a recovery alert has been issued. | [16 empty] | ー
115 | XXX Management | Close | improvement | ー | subject | 2024-09-19 |  | ー | ー | BB | BB | AA Ms. MM Ms. NN | ー | high |  |  |  | Gabakura Resources + Cost Summary Especially Aurora and ECS | [17 empty] | ー
116 | XXX Management | New | XX Maintenance | ー | subject | 2024-09-19 |  | ー | ー | GG | GG |  | ー | ⁠ |  |  | Creating a Relay VPC | The stock of "Relay VPC" used when setting up the NW from XX organizations has been depleted, so it is necessary to create it (as of September 19, 2024, there are 4 left) The construction procedure was presented by XX, but it is a procedure to create with CDK ◆ Procedure manual storage folder \\luna-fs\025\XX Management (FY2022~)\01_Development PJ\35_Infrastructure Environment Design and Construction\00_Management\90_Takeover Management\Other Important Documents\Add Relay VPC ◆ File Additional relay VPC_r2.xlsx | ■2024/10/08 BB DirectCoYY Connection/IpSecVPN Connect Organizations should check as soon as possible. | [16 empty] | ー
117 | XXX Management | Supported by | policy | ー | subject | 2024-09-24 |  | ー | ー | BB |  |  |  | middle |  |  |  | Measures of XX Company | ■2024/10/08 BB Renovation and confirmation have already been set up as SNS subscriptions. The production has been revered, but it has been rejected by the Digi Agency and is being confirmed. (at XX company) ---------------- SNS Subscription Additional Settings ⇒ for the time being, renovation / confirmation is handled by procedure. * What is the design document? If it's permanent, you have to build it with CDK. | [16 empty] | ー
118 | XXX Management | New | XX Maintenance | ー | subject | 2024-09-24 |  | ー | ー | DD |  |  | ー | low |  | Creating a Relay VPC |  | Sorting out document and environment differences | Since there are some differences between the actual environment and the environment definition document, it is necessary to prepare the documentation from the following perspectives. - Modify the environmental differences according to the actual environment. ・ If there is a description in the environment and not in the design document, check whether it is stored in a procedure manual. | [16 empty] | ー
119 | XXX Management | New | XX Maintenance | ー | subject | 2024-10-01 |  |  | Operation Tm: OO | DD |  | Operational Tm | ー | middle |  |  |  | Stopping and starting jobs in EventBridge in the operation procedure | 2024/10/01 DD Some additional work was required in ZZ's operation procedure, and it was necessary to stop and start the job in EventBridge. At present, I have heard that the work seems to be the authority of only the foundation members, and the proposal is 1. Have only that part implemented on the foundation 2. Who is in charge of the current operation? Grant EventBridge operation permissions to a role in ３． Assign the role of infrastructure officer to the person in charge of infrastructure at ZZ Company I feel like it's going to be about that, but I think 1 is tough because it's mainly work that occurs during xxxx maintenance and will be available on Saturdays and Sundays. I would like to consult with you about the relationship between the current EventBridge permissions and each role, and what to do as a response, such as 2, 3 (or other methods). | [16 empty] | ー
120 | XXX Management | New | XX Maintenance | ー | subject | 2024-10-01 |  |  | Operation Tm: OO | DD |  | ー | ー | middle |  |  |  | I want to change the execution time of the job at the beginning of the year. | 2024/10/01 DD Details will be heard in the future | [16 empty] | ー
121 | XXX Management | New | XX Maintenance | ー | subject | 2024-10-01 |  |  | - | BB |  | ー | ー | middle |  |  |  | There are VPCs that do not have a VPC flow log output. | The error is due to the fact that the output directory of the VPC flow log of vp201a1 (for the relay VPC Myna Portal) does not exist. | [16 empty] | ー
122 | XXX Management | Close | XX Maintenance | ー | subject | 2024-10-01 |  |  | - | BB | BB | ー | 13148 | middle |  |  |  | ガバクラ依頼-AWSComputeOptimizer有効化 | ■2024/10/04 BB Production, renovation, and customer service completed The following request ----- requested by Gabakura------ September 20, 2024 In charge of Government Cloud Requisition of work for resource optimization 1. Purpose of implementation In the use of government clouds, modernization is a condition of use, and we are seeking to continuously optimize the resources used through performance management. The purpose of this meeting is to focus on resource optimization, confirm the implementation status, and if appropriate management is not possible, promptly implement resource optimization, and reflect the results in the budget for FY7 Reiwa. 2. Outline of Implementation Implement cost reduction measures for services on the designated CSP The cost reduction method is to optimize computing resources (CPU, memory, etc.) In order to streamline resource optimization decisions, it is recommended to use "Compute Optimizer" 3. Eligibility Among government information systems that use the government cloud, the system with a relatively high cloud usage cost (Appendix) The target resources for optimization are the following three services in the production environment. ECS Services (Fargate) EC2 Instances RDS RDS（Aurora） 4. Deadline for implementation Friday, September 27, 2024 Submissions If the resource is optimized: Recommendations by resource results When resource optimization is required: (1) Theoretical annual savings (in dollars) for resizable resources. (2) Work implementation plan (in October), (3) Optimized screen capture or output result by CLI * If it takes time to consider and implement, please consult separately with the reason. 5. In-depth approach ■ For target resources other than Aurora * For detailed instructions on Compute Optimizer, please refer to the official AWS User Guide (xxxxdocs.aws.amazon.com/ja_jp/compute-optimizer/latest/ug/what-is-compute-optimizer.html) Opt-in to Compute Optimizer for all AWS accounts running production environments (not required if you've already opted in) It takes up to 12 hours to make a recommendation. Review recommendations by resource From the recommendation page for the target resource type, verify that the target resource is displayed Filter by "Result = Over-provisioning" If the target resource does not exist as a result of the filter, no further work is required if all target resources are displayed by filtering with "result = optimized". Export the results. Downsizing Considerations Learn more about recommendations from each resource See recommended options, savings, CPU usage, and more Select the instance type and size to be changed, the CPU size of the task, etc. Planning Your Resizing Efforts PJMO and vendor discuss and formulate a work plan and present it to the Digital Agency. If it is difficult to carry out the change work in the near future, please provide an approximate work schedule that can be carried out If it is not possible to change the change at any time, please tell us the reason Confirmation and presentation of cost savings due to resizing Aggregate the theoretical annual savings in dollars for resizable resources Implementation of work After completing the work, Compute Optimizer confirms that the result of the target resource has been changed to "optimized". Optimized screen capture or CLI output results presented to the Digital Agency ■ For Aurora Checking the usage status of Aurora Check CPU usage, database load, etc. from Cloud Watch metrics, Performance Insight, etc., and comprehensively check the usage status Analyzing Resizing Consider whether it is possible to change the DB instance type and size from the data confirmed in step 1. As a rule of thumb, if CPU usage is less than 30% on average, there is a high possibility of over-provisioning. Choosing the Best DB Instance Type Planning Your Resizing Efforts PJMO and vendor discuss and formulate a work plan and present it to the Digital Agency. If it is difficult to carry out the change work in the near future, please provide an approximate work schedule that can be carried out If it is not possible to change the change at any time, please tell us the reason Confirmation and presentation of cost savings due to resizing Aggregate the theoretical annual savings in dollars for resizable resources Implementation of work Capture of Aurora instance type before and after change or presentation of CLI output results to Digital Agency 5. Future Plans Please refer to the GCAS Guide ** "Forecast and Actual Management and Optimization of Cloud Usage Charges (AWS)" ** to continuously implement cost optimization. This request is limited to resource optimization (appropriate sizing), but we would like to ask you to enable the "Cost Optimization Hub" in each AWS account and actively implement the other recommended actions presented. In addition, in the budget request for the next fiscal year, the implementation status of the cost optimization (results of recommendations, etc.) will be attached at the time of application. (Appendix) Target Systems e-Gov Information Provision Record Disclosure System Service search and electronic application function system (one-stop service for incorporation) △△ etc. Information linkage and utilization system Common Information Retrieval System Establishment of a system for the realization of the Smartphone Implementation of the My Number Card function Real Estate Registry-Based Registry GovBot Common Government Website Digital Certificates & Signatures | [16 empty] | ー
123 | XXX Management | Close | XX Maintenance | ー | subject | 2024-10-01 |  |  | - | BB | DD | Mr. PP QQ | ー |  |  |  |  | AD User Password Reset Request | Correspondence completed | [16 empty] | ー
124 | XXX Management | Close | XX Maintenance | ー | subject | 2024-10-01 |  |  | - | BB | BB | Mr. PP QQ | ー |  |  |  |  | WorkSpace起動依頼 | Correspondence completed | [16 empty] | ー
125 | XXX Management | New | XX Maintenance | ー | subject | 2024-10-08 |  | 2024-10-14 |  | BB |  |  | 13336 |  |  |  |  | 13336 [ZNTM-96] Request for IP drilling of verification site | [17 empty] | ー
126 | [35 empty] | ー
127 | [35 empty] | ー
128 | [35 empty] | ー
129 | [35 empty] | ー
130 | [35 empty] | ー
131 | [35 empty] | ー
132 | [35 empty] | ー
133 | [35 empty] | ー
134 | [35 empty] | ー
135 | [35 empty] | ー
136 | [35 empty] | ー
137 | [35 empty] | ー
138 | [35 empty] | ー
139 | [35 empty] | ー
140 | [35 empty] | ー
141 | [35 empty] | ー
142 | [35 empty] | ー
143 | [35 empty] | ー
- | - | - |  | - | - | - | - | - |  | - | [7 empty] | - | - | - | - |  | - | - | - |  |  | - | - | - | - | - | - | - | - | ー

## Pile of work (Toyosu 5F) (For N (hidden)
|  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9
|  | 2 |  |  |  | 4.5 |  |  |  | 5.5 |  |  |  | 8 |  |  |  | 8 |  |  |  | 8
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
National Qualification Management SYS | Otherta
Commencement of operation: Priority monitoring correspondence
Handling of the advanced shrine hall: Second stage work
Handling of the Advanced Shrine Temple: Remaining Issues
Advanced Shrine Winding Correspondence: Batch Execution Method Improvement Response
Infrastructure Maintenance and Maintenance Support
Overall configuration diagram (bird's-eye view) correspondence Zentai
CICD Improvement Response
Support for replication environment construction
SWA-ITA Measures | Otherta
Public Service Mesh PoC Construction Support
SWA-ITA Measures
XXXXX | XXXXXXX
XXXXXXX
Ito
Contents unconfirmed
Network connection work with external SYS
Confirmation of NW communication with circumscribed SYS
Changing the CloudWatch log backup method
Changing the Aurora Statistics Backup Method
Batch execution method study
Design/Implementation/Testing (Unit/Combination)
Contents unconfirmed
AWS Bird's-eye View Creation
Contents unconfirmed
Contents unconfirmed
CDK Implementation
construction
test
Consideration of measures
Implementation of measures
Implementation of measures
It depends on the content of the measures, but I don't think it can be done all at once, so why not divide it into phases?
Enomoto 1.0 man-month/month
Horizumi
Seto 1.0 man-months/month
Hashimoto
strait
strait
Hashimoto
Horizumi
Enomoto
Horizumi 1.0 man-month/month
Hashimoto 0.8 man-months/month
Chiba 1.0 man-month/month
Chiba
Enomoto
strait
A
A 1.0 man-month/month
Implementation of measures
Implementation of measures
★ Please let us consult with you about whether Hitachi will handle it, including the contents.
<Assumed work>
- Writing of priority monitoring plans
- Writing of priority monitoring schedules and systems
- Writing of priority monitoring procedures
・Priority Monitoring Report
・Rehearsal
Ito 0.5 man-months/month
B 1.0 man-month/month
It is said that the procedure manual has been prepared→ the procedure contents are confirmed.
Including communication day adjustment?
Includes design/build/test/release
→ Production environment, renovation confirmation environment, connection confirmation environment, integration test environment
Includes design/build/test/release
→ Production environment, renovation confirmation environment, connection confirmation environment, integration test environment
It is said that the procedure manual has been prepared→ the procedure contents are confirmed.
Rest of the environment construction & testing
→ Production environment / Renovation confirmation environment / Connection check environment / Integration test environment
Batch Execution Method Improvement + Public Service Mesh PoC + ITA Measures Consideration
+ AWS Overall Configuration Diagram
Concurrently serves as
Batch Execution Method Improvement + Public Service Mesh PoC + ITA Measures Consideration
+ AWS Overall Configuration Diagram
Concurrently serves as
Hashimoto
Batch Execution Method Improvement + Public Service Mesh PoC + ITA Measures Consideration
+ AWS Overall Configuration Diagram
Concurrently serves as
Batch Execution Method Improvement + Public Service Mesh PoC + ITA Measures Consideration
+ AWS Overall Configuration Diagram
Concurrently serves as
B
★ Confirmation of maintenance details
From the writing of → procedures / operating rules?
★MJ200000000000000000000
★ Please let us consult with you about whether Hitachi will handle it, including the contents.
★ Please let us consult with you about whether Hitachi will handle it, including the contents.
★MJ200000000000000000000
The main charge is MJ (method study, etc.) → corresponding to the construction part
Concurrent position with National Qualification Maintenance
Concurrent position with National Qualification Maintenance
CICD Study
Chiba
A
B
Concurrently served as a national qualification CICD for SWA-ITA measures
Concurrently served as a national qualification CICD for SWA-ITA measures
Ito

## 【Cannot be changed】List Master
classification |  | Category | Target | Status | Display Range | Classification
The Big Challenge | Issues that affect the main line table (drafted in the project issue table) | Requirement Definition | ー | New | for customers | Subject | Once the cause is known, break the problem into tasks that can be solved by one person. Assign an owner and deadline, adjust the response start date, and record it in the WBS.
Medium Issues | Issues that affect the midline table, business requirements across teams, and quality issues | Basic design | ー | Supported By | for the Interior | Inquiry Received | Inquiries from other teams. Break down into tasks for one person, assign owner and deadline, then move to task.
Small Assignments | Issues that affect the WBS or that require coordination within the team | Detailed design | ー | On Hold | ー | Incident Response | Commercial incident response. Break down the problem, assign owner and deadline, adjust start date, and record in WBS.
|  | construction | ー | Pending Approval | ー | Work Request Received | Break down the problem, assign owner and deadline, adjust start date, and record in WBS.
|  | test | ー | Closed | ー | Meeting Request Received
|  | application | ー | Withdrawn | ー | Review Request Received
|  | ー | ー | Task Assigned (Start Time Pending) | ー | Task (Work Request Received)
|  | ー | ー | WBS Converted To Closed | ー | Task
|  | ー | ー | WBS Conversion To Supported | ー
|  | ー | ー |  | ー
subject
Query
Incident Response
WBS
Work Requests
Request for a meeting
Request a Review
Close
When the task is completed, it is converted to WBS.
When the task is completed, it is converted to WBS.
If it is completed on the same day, it will be carried out without converting it to WBS.

## 20241010_NT Meeting
Meeting Recap – 2024/10/10 Attendees: BB, Hashimoto, DD, XX company rep Key Discussion Points & Actions: Relay VPC Creation: BB reported that the stock of Relay VPCs is running low (only 4 left as of 9/19/2024). The team agreed to proceed with creating a new Relay VPC using the CDK procedure. Action: BB to initiate creation and update the procedure manual. Due: 2024/10/20 SNS Subscription Additional Settings: XX company has set up renovation and confirmation as SNS subscriptions, but production was rejected by the Digi Agency. Action: Hashimoto to confirm the design document and coordinate with XX company for permanent setup. Due: 2024/10/18 Document/Environment Differences: There are discrepancies between the actual environment and the environment definition document. Action: BB to prepare updated documentation and check if missing items are stored in the procedure manual. Due: 2024/10/25 EventBridge Job Operation: Additional work is needed in ZZ’s operation procedure for stopping/starting jobs in EventBridge. Action: DD to consult with the foundation team about permissions and clarify the process for future operations. Due: 2024/10/22

## OLD Credential Management - Dig (hidden)
| Use this worksheet to create a schedule for your project. In cell B1, type the title of this project. Information about how to use this worksheet, such as screen reader descriptions and workbook authors, is in the More Information worksheet. If you keep moving column A down, you'll see more information. |  |  | [National Qualification Management System] | [19 empty] | Simple Gantt Chart (Vertex42.com)
|  | Chiba |  | Hashimoto | [19 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
|  | Enomoto Enomoto |  | Seto |  |  |  |  | Project Initiation: | [9 empty] | 2025-06-14
|  | Horizumi |  | ⁠ |  |  |  |  | Week Display: | [9 empty] | 2 |  |  |  |  | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME?
| Cells I5 through BL5 contain the number of the day of the week that appears in the cell block above each date cell, and is automatically calculated. Do not change these cells. Today's date is enclosed in red (hexadecimal #AD3815) throughout the entire date column from today's date in row 5 to the end of the project schedule. | [22 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| This line contains the schedule heading for the project that follows it. To read the content aloud, go from B6 to BL 6. The first character of each day of the week on the date above the heading starts in cell I6 and continues through cell BL6. Timeline charts for all projects are auto-generated based on the start and end dates entered, using conditional formatting. Do not change the contents of the cells in column I and subsequent columns, starting with cell I7. |  |  | task |  |  | Details: | Person in charge: |  | inside Reviewer | ND Reviewer | remarks | Progress | Appointment | Achievements | Unit | inside RV Completion Date | ND RV Completion Date | schedule |  | achievements |  | days | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Do not delete this line. This row is hidden to hold the formula that is used to highlight the current date in the project's schedule. | [12 empty] | Scale | Scale |  |  |  | start date | End Date | start date | End Date | #NAME? | [21 empty] | ▲ | [35 empty] | ▲
B | 1 |  |  | Digital Certificate Compatible
B | 1 | 1 |  |  | Requirement Definition
B | 1 | 1 | 1 |  |  | Requirement Definition Document |  |  | Chiba | [8 empty] | ー | 2024-06-12 | 2024-06-14
B | 1 | 1 |  |  | Basic Design
B | 1 | 1 | 2 |  |  | Basic Design |  |  | Chiba | [8 empty] | ー | 2024-06-17 | 2024-06-21
B | [5 empty] | Design + Manufacture + Construction
B | [5 empty] | 【IT environment (for KMS/HSM)】CDK definition document writing |  |  | Horizumi | [9 empty] | 2024-06-12 | 2024-06-18
B | [5 empty] | 【IT Environment (for KMS/HSM)】Implementation/Deployment |  |  | Horizumi | [9 empty] | 2024-06-19 | 2024-06-25
B | [5 empty] | [Duplicate (1) (for KMS/HSM)] CDK definition document writing Fukusei |  |  | Chiba | [9 empty] | 2024-06-24 | 2024-06-28
B | [5 empty] | [Replication (1) (for KMS/HSM)] Implementation/Deployment |  |  | Chiba | [9 empty] | 2024-07-01 | 2024-07-05
B | [5 empty] | 【Renovation confirmation environment (for KMS/HSM)】CSR / Key Pair Creation |  |  | ⁠ | [9 empty] | 2024-06-17 | 2024-06-19
B | [5 empty] | 【Connection check environment (for KMS/HSM)】CSR / Key Pair Creation |  |  | ⁠ | [9 empty] | 2024-06-17 | 2024-06-19
B | [5 empty] | [Production environment (for KMS/HSM)] CSR / Key Pair Creation |  |  | ⁠ | [9 empty] | 2024-06-17 | 2024-06-19
B | [5 empty] | 【Renovation Confirmation Environment (for KMS/HSM)】Writing of CDK definition book |  |  | ⁠ | [9 empty] | 2024-06-12 | 2024-06-18
B | [5 empty] | 【Renovation confirmation environment (for KMS/HSM)】Implementation/Deployment |  |  | ⁠ | [9 empty] | 2024-06-19 | 2024-06-21
B | [5 empty] | 【Connection Confirmation Environment (for KMS/HSM)】Writing of CDK definition book |  |  | ⁠ | [9 empty] | 2024-07-03 | 2024-07-09
B | [5 empty] | [Connection confirmation environment (for KMS/HSM)] Implementation/deployment |  |  | ⁠ | [9 empty] | 2024-07-10 | 2024-07-12
B | [5 empty] | [Production environment (for KMS/HSM)] Writing CDK definition documents |  |  | ⁠ | [9 empty] | 2024-06-24 | 2024-06-28
B | [5 empty] | [Production environment (for KMS/HSM)] Implementation/Deployment |  |  | ⁠ | [9 empty] | 2024-07-01 | 2024-07-02
B | [5 empty] | Test
B | [5 empty] | 【IT environment (for KMS/HSM)】Unit test item creation |  |  | Seto | [9 empty] | 2024-06-24 | 2024-06-26
B | [5 empty] | 【IT Environment (for KMS/HSM)】Unit Test (Digestion) |  |  | Seto | [9 empty] | 2024-06-27 | 2024-07-01
B | [5 empty] | 【IT Environment (for KMS/HSM)】Binding test item creation |  |  | Horizumi | [9 empty] | 2024-06-26 | 2024-07-02
B | [5 empty] | 【IT Environment (for KMS/HSM)】Bondage Test (Digestion) |  |  | Horizumi | [9 empty] | 2024-07-03 | 2024-07-05
B | [5 empty] | 【Duplication (1)(for KMS/HSM)】Unit test (digestion) | [12 empty] | 2024-07-15 | 2024-07-17
B | [5 empty] | 【Duplication (1)(for KMS/HSM)】Binding test (digestion) | [12 empty] | 2024-07-18 | 2024-07-23
B | [5 empty] | [Modification confirmation environment (for KMS/HSM)] Unit test (digestion) | [12 empty] | 2024-07-02 | 2024-07-04
B | [5 empty] | 【Modification confirmation environment (for KMS/HSM)】Bondage test (digestion) | [12 empty] | 2024-07-05 | 2024-07-09
B | [5 empty] | [Connection confirmation environment (for KMS/HSM)] Unit test (digestion) | [12 empty] | 2024-07-10 | 2024-07-12
B | [5 empty] | [Connection confirmation environment (for KMS/HSM)] Integration test (digestion) | [12 empty] | 2024-07-15 | 2024-07-17
B | [5 empty] | [Production environment (for KMS/HSM)] Unit test (digestion) | [12 empty] | 2024-07-05 | 2024-07-09
B | [5 empty] | [Production environment (for KMS/HSM)] Integration test (digestion) | [12 empty] | 2024-07-10 | 2024-07-12
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
B
| This is an empty line | [21 empty] | #NAME?
| This line represents the end of the project's schedule. Do not enter anything in this line. Insert a new line above this line to continue creating the schedule for the project. |  |  | Insert a new line above this line | [18 empty] | #NAME?
Group Liberation
Personal emancipation

## WBS (Other) (hidden)
Use this worksheet to create a schedule for your project. In cell B1, type the title of this project. Information about how to use this worksheet, such as screen reader descriptions and workbook authors, is in the More Information worksheet. If you keep moving column A down, you'll see more information. |  | 【National Qualification Management System / SWA-ITA (Public Service Mesh)】 | [18 empty] | Simple Gantt Chart (Vertex42.com)
| Chiba |  | Hashimoto | [17 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
| Enomoto Enomoto |  | Seto |  |  | Project Initiation: | [9 empty] | 2025-06-14
| Horizumi |  | ⁠ |  |  | Week Display: | [9 empty] | 2 |  |  |  |  | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME?
Cells I5 through BL5 contain the number of the day of the week that appears in the cell block above each date cell, and is automatically calculated. Do not change these cells. Today's date is enclosed in red (hexadecimal #AD3815) throughout the entire date column from today's date in row 5 to the end of the project schedule. | [20 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
This line contains the schedule heading for the project that follows it. To read the content aloud, go from B6 to BL 6. The first character of each day of the week on the date above the heading starts in cell I6 and continues through cell BL6. Timeline charts for all projects are auto-generated based on the start and end dates entered, using conditional formatting. Do not change the contents of the cells in column I and subsequent columns, starting with cell I7. |  | task |  |  | Details: | Person in charge: | inside Reviewer | ND Reviewer | Remarks: | Progress | Appointment | Achievements | Unit | inside RV Completion Date | ND RV Completion Date | schedule |  | achievements |  | days | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Do not delete this line. This row is hidden to hold the formula that is used to highlight the current date in the project's schedule. | [10 empty] | Scale | Scale |  |  |  | start date | End Date | start date | End Date | #NAME?
SWA-ITA
setup
|  |  |  | ・Remote connection application, etc. |  | All Zenin
|  |  |  | ・Teasm追加依頼(資格管理/SWA-ITA/公共SM) |  | All Zenin
|  |  |  | ・PMWB (Qualification Management) |  | All Zenin
|  |  |  | - File server access request (qualification management) |  | All Zenin
|  |  |  | ・AWS IAM user withdrawal request (entitlement management) |  | All Zenin
|  |  |  | - GitHubCopilot登録 (資格管理/SWA-ITA) |  | All Zenin
|  |  |  | ・PCS申請(SWA-ENG) |  | All Zenin
|  |  |  | ・開発BXO申請(SWA-ITA) |  | All Zenin
|  |  |  | ・OAインストール(VSCode/sakura/teraterm/Vicio/MSProject/VSCode) |  | All Zenin
|  |  |  | ・GitHubCopilot:LanguagePac |  | All Zenin
|  |  |  | ・GitHubCopilot:Git |  | All Zenin
|  |  |  | ・GitHubCopilot:Maven |  | All Zenin
|  |  |  | ・GitHubCopilot:python |  | All Zenin
|  |  |  | ・GitHubCopilot:Java |  | All Zenin
|  |  |  | ・GitHubCopilot:Node.js |  | All Zenin
|  |  |  | ・GitHubCopilot:TypeScript |  | All Zenin
|  |  |  | ・GitHubCopilot:GitHubCopilot |  | All Zenin
|  |  |  | ・GitHubCopilot: PlantUML * Used to write UML using PlantUML in VSCode |  | All Zenin
|  |  |  | ・GitHub Copilot: Markdown Preview Enhanced * Used to embed PlantUML UML in Markdown documents |  | All Zenin
|  |  |  | ・GitHubCopilot: Indent-rainbow * Indent w easy-to-understand display |  | All Zenin
|  |  |  | ・GitHubCopilot: Prettier * Code format |  | All Zenin
|  |  |  | ・GitHubCopilot: Bracket Pair Colorization Toggler |  | All Zenin
|  |  |  | ・GitHubCopilot: Better Comments |  | All Zenin
|  |  |  | ・GitHubCopilot: advanced-new-file * Create a file / folder from the command palette |  | All Zenin
|  |  |  | ・GitHubCopilot: HTML CSS Support * Complements IDs and Classes |  | All Zenin
|  |  |  | ・GitHubCopilot: Foam * VSCode becomes a further memo app |  | All Zenin
|  |  |  | ・GitHubCopilot: Project Manager * Organize multiple projects |  | All Zenin
|  |  |  | ・ GitHub Copilot: Todo Tree * Lists TODOs |  | All Zenin
|  |  |  | ・GitHubCopilot: Git Graph * Display Git in a graph |  | All Zenin
|  |  |  | ・GitHubCopilot: GitLens * Git extension such as easy git operation with GUI |  | All Zenin
|  |  |  | ・ GitHubCopilot: Bonus: vscode-pets * You can keep a cat in the editor |  | All Zenin
Setup InstructionsCreated
・Remote connection application, etc.
・Teasm追加依頼(資格管理/SWA-ITA/公共SM)
・PMWB (Qualification Management)
- File server access request (qualification management)
・AWS IAM user withdrawal request (entitlement management)
- GitHubCopilot登録 (資格管理/SWA-ITA)
・PCS申請(SWA-ENG)
・開発BXO申請(SWA-ITA)
・OAインストール(VSCode/sakura/teraterm/Vicio/MSProject/VSCode)
・GitHubCopilot:LanguagePac
・GitHubCopilot:Git
・GitHubCopilot:Maven
・GitHubCopilot:python
・GitHubCopilot:Java
・GitHubCopilot:Node.js
・GitHubCopilot:TypeScript
・GitHubCopilot:GitHubCopilot
・GitHubCopilot: PlantUML * Used to write UML using PlantUML in VSCode
・GitHub Copilot: Markdown Preview Enhanced * Used to embed PlantUML UML in Markdown documents
・GitHubCopilot: Indent-rainbow * Indent w easy-to-understand display
・GitHubCopilot: Prettier * Code format
・GitHubCopilot: Bracket Pair Colorization Toggler
・GitHubCopilot: Better Comments
・GitHubCopilot: advanced-new-file * Create a file / folder from the command palette
・GitHubCopilot: HTML CSS Support * Complements IDs and Classes
・GitHubCopilot: Foam * VSCode becomes a further memo app
・GitHubCopilot: Project Manager * Organize multiple projects
・ GitHub Copilot: Todo Tree * Lists TODOs
・GitHubCopilot: Git Graph * Display Git in a graph
・GitHubCopilot: GitLens * Git extension such as easy git operation with GUI
・ GitHubCopilot: Bonus: vscode-pets * You can keep a cat in the editor
|  |  | Mr. Moro's homework Moro | [16 empty] | #NAME?
|  |  |  | I want to put the latest version of Redis (in-memory) on Windows. |  | Hashimoto |  |  | If it is an older version, you can manually install the Windows version. ⇒ want to put the latest version in WSL. | completion | [7 empty] | 2024-04-23 | 2024-04-23
|  |  |  | I want to put WSL in BXO. |  | Hashimoto |  |  | When installing WSL, I get stuck in a proxy. ⇒ can be downloaded and installed manually. ⇒However, it cannot be booted unless CPU virtual is enabled in the BIOS of BXO.) | completion | [7 empty] | 2024-04-23 | 2024-04-23
|  |  |  | Can CDK dynamic testing be automated? |  | Hashimoto
National Qualification
Understanding the system
Grasp of the meeting body
Document Management Tracking
Understanding the composition of the environment
Process grasp
Release method (AP/Substrate) grasp
Monitoring Grasp
Overall Composition Grasp
Job Grasp
Operational Understanding (Structure/Procedure)
Overall Schedule Grasp
This is an empty line | [19 empty] | #NAME?
This line represents the end of the project's schedule. Do not enter anything in this line. Insert a new line above this line to continue creating the schedule for the project. |  | Insert a new line above this line | [17 empty] | #NAME?

## WBS(SWA-ITA) (hidden)
Use this worksheet to create a schedule for your project. In cell B1, type the title of this project. Information about how to use this worksheet, such as screen reader descriptions and workbook authors, is in the More Information worksheet. If you keep moving column A down, you'll see more information. |  | 【SWA-ITA】 | [18 empty] | Simple Gantt Chart (Vertex42.com)
| Chiba | Hashimoto | [18 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
| Enomoto Enomoto | Seto |  |  |  | Project Initiation: | [9 empty] | 2025-06-14
| Horizumi | ⁠ |  |  |  | Week Display: | [9 empty] | 2 |  |  |  |  | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME? | [6 empty] | #NAME?
Cells I5 through BL5 contain the number of the day of the week that appears in the cell block above each date cell, and is automatically calculated. Do not change these cells. Today's date is enclosed in red (hexadecimal #AD3815) throughout the entire date column from today's date in row 5 to the end of the project schedule. | [20 empty] | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
This line contains the schedule heading for the project that follows it. To read the content aloud, go from B6 to BL 6. The first character of each day of the week on the date above the heading starts in cell I6 and continues through cell BL6. Timeline charts for all projects are auto-generated based on the start and end dates entered, using conditional formatting. Do not change the contents of the cells in column I and subsequent columns, starting with cell I7. |  | task |  |  | Details: | Person in charge: | inside Reviewer | ND Reviewer | Remarks: | Progress | Appointment | Achievements | Unit | inside RV Completion Date | ND RV Completion Date | schedule |  | achievements |  | days | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Do not delete this line. This row is hidden to hold the formula that is used to highlight the current date in the project's schedule. | [10 empty] | Scale | Scale |  |  |  | start date | End Date | start date | End Date | #NAME?
SWA-ITA (Public Service Mesh POC6)
Confirmation of materials Shiryo
|  |  |  | Confirmation of materials Shiryo | [11 empty] | 2024-04-15 | 2024-04-19
|  |  |  | PoC5 / Public Technical Destination Asset Confirmation | [11 empty] | 2024-04-15 | 2024-04-19
CDK Manufacturing
|  |  |  | CDK Manufacturing (around Aurora) |  | Seto |  |  | 【Work content】From CDK manufacturing to compilation, when the development BXO/PCS is ready, it will be deployed ⇒ provisioned. | completion | [5 empty] | 2024-04-23 | 2024-04-26 | 2024-04-23
|  |  |  | CDK manufacturing (around Dynamao) |  | Seto |  |  | 【Work content】From CDK manufacturing to compilation, when the development BXO/PCS is ready, it will be deployed ⇒ provisioned. | completion | [5 empty] | 2024-04-23 | 2024-04-26 | 2024-04-23
|  |  |  | Building on PCS (around Auora) |  | Seto |  |  |  | completion | [5 empty] | 2024-05-07 | 2024-05-10
|  |  |  | Building on PCS (around Dynamo) |  | Seto |  |  |  | completion | [5 empty] | 2024-05-07 | 2024-05-10
|  |  |  | Inventory of issues in construction using Gabakura assets |  | Seto |  |  | ・ After internal confirmation, deploy to NTTD | completion | [5 empty] | 2024-06-05 | 2024-06-06 | 2024-06-03 | 2024-06-05
Building around the ECS
|  |  |  | ECS,ECR,CodePipeline,Codebuild,S3 |  | Seto |  |  |  | completion
|  |  |  | Parameter extraction for PCS environments |  | Seto |  |  |  | completion | [5 empty] | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01
SWA-ITA(施策)
(1) [Manufacturing ⇒ construction] Assist in the development of cloud environment (AWS) CDK through Github Copilot. Gabakura Asset
|  |  |  | Sorting out AWS services that can be manufactured with CDK (also confirming what can and cannot be done) |  | Seto | [9 empty] | TBD
|  |  |  | CDK Overview from manufacturing to provisioningDocumentation |  | Seto | [9 empty] | TBD
|  |  |  | CDK Procedure from manufacturing to provisioningCreation |  | Seto | [9 empty] | TBD
|  |  | (2) [Parameter design ⇒ manufacturing] Create guidelines for design documents → source code. (Not only when creating a new one, but also including how to reflect the source code when modifying the design) | [5 empty] | on the premise of CDK implementation
Creation of source code generation guidelines from design documents
Parameter design document format creation for AWS services: Aurora
Parameter design document format creation for AWS services: Dunamo
Parameter design document format creation for AWS services: S3
Parameter design document format creation for AWS services: EC2
Parameter design document format creation for AWS services: AM
Parameter design document format creation for AWS services: CS
Parameter design document format creation for AWS services: Lambda
Parameter design document format creation for AWS services: CloudwatchLogs
Parameter design document format creation for AWS services: EventBrige
Parameter design document format creation for AWS services: CloudwatchAgent
Parameter design document format creation for AWS services: CloudwatchAlerm
Parameter design document format creation for AWS services: Cloudwatch metrics
Parameter Design Document Format Creation for AWS Services: KMS
Parameter design document format creation for AWS services: SQS
Parameter design document format creation for AWS services: SNS
Parameter design document format creation for AWS services: ALB
Parameter design document format creation for AWS services: VPN endpoints
Parameter design document format creation for AWS services: Batch
Parameter design document format creation for AWS services: StepFunction
Parameter design document format creation for AWS EC2: EC2 (RHEL8)
Creation of parameter design document format for AWSEC2: EC2 (WindowsodwsXX)
Creation of AWS EC2 parameter design document format: EC2 (Apache)
Creation of AWSEC2 parameter design document format: EC2 (tomcat)
(3) [Requirement Definition ⇒ Basic Design] Guideline
Template for creating an overall configuration diagram from the service used (MSCopilot)
(4) [Basic design ⇒ detailed design] Guideline
(5) [Unit test (parameter actual machine design document matching)] Automation guideline
(6) [Unit test (basic operation check)] Automation guideline
(7) [Integration test 1 (between services of the same tenant * including cross-region testing)] Automation guideline
(8) [Integration test 2 (between multi-tenant services * including cross-region crossing)] Automation guideline
Other: Meetings, etc.
This is an empty line | [19 empty] | #NAME?
This line represents the end of the project's schedule. Do not enter anything in this line. Insert a new line above this line to continue creating the schedule for the project. |  | Insert a new line above this line | [17 empty] | #NAME?