## Sheet1
Work Item | Owner | Progress | Blockers | Link | ETA
Define Proposed Tools
Enumerate proposed tools | Sandy + Joaquín | Done |  | Tools in Moonshot.docx
Scenario examples for tools | Sandy + Joaquín | In progress | More examples from DKI; datasets for all examples; check compliance on datasets | Analysis Tool Example Cases.xlsx
April Intent Analysis
Align on which tools to include
Evaluate scenario examples (ad hoc) | AD Crew | In progress
Align on Python vs native preference
User research on Answers | Pradeep + Avani |  |  |  | 2025-05-16
Tools forum with AA team | Maya
Align on answer vs artifact preference
User research | Pradeep | In progress |  |  | 2025-05-16
Align on how to integrate tools | Joaquín + Moonshot ENG |  |  | Tools Loop
Prototype of tools in Orkney (text analysis) | Marian | Not started
Prototype of fake JS APIs in Orkney (text analysis) | Alexander | Not started | Need guidance on where to start from Moonshot crew
Compare prototypes | AD + Moonshot ENG | Not started
On grid (separate from Moonshot)
Plan text analysis on grid flow | Sandy
Eval and fine tuning for AD/TA | Struan
Full coverage test of existing AD cases | Natasha, Raquel, Juan
Analysis benchMayak for complex analysis queries | Jiang |  |  |  | TBD
Analysis benchmark for complex sheet data | Jiang |  |  |  | 2 weeks (data ready)
Coordinate with PROSE on fine tuning needs for analysis | AD Crew + Yvonne
Work on tool coverage / quality
Optimize service for tools | Alex
Determine if multi table support is needed | Joaquín + Alex + Sandy
Investigate other needs
Story for analysis tools across Copilots | ?? |  |  |  | FY26
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: When you do this investigation, please capture enough details so they can be repeated in the future - we should be getting these scenarios integrated into our overall eval datasets so they're repeatable and we have a shared understanding of coverage and needed capabilitiles